## Tickets
Issue Key | Issue Type | Summary | Description | Status | Resolution | Priority | Component | Labels | Assignee | Reporter | Sprint | Story Points | Epic Link | Fix Version | Created | Updated | Resolved | Due Date | Comment Count | Comments
PROJ-1001 | Story | As a user, I want improved checkout | As a user, I want checkout to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Progress | Unresolved | Low | Payments | customer-reported | Priya Sharma | Chloe Nguyen |  | 8 | PROJ-1084 |  | 2026-09-14 15:02 | 2026-09-15 16:02 |  | 2026-09-27 | 5 | [2026-09-15 19:02] Chloe Nguyen: Code review done, left a few minor comments. LGTM otherwise. [2026-09-16 10:02] Chloe Nguyen: Could not reproduce on latest build. Can the reporter confirm? [2026-09-18 10:02] Sofia Rossi: Design mockups attached. Please review before we start. [2026-09-18 16:02] Lucas Martin: Looping in Sofia Rossi since they own this area. [2026-09-20 23:02] Daniel Ortiz: Root cause: missing null check when the payments config is not loaded.
PROJ-1002 | Story | Add audit logging to push notifications | Compliance requires that every action in push notifications is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Won't Do | Won't Fix | Medium | Notifications | performance, customer-reported, regression | Sofia Rossi | Chloe Nguyen | Sprint 44 | 8 |  |  | 2026-08-11 09:14 | 2026-08-25 09:14 | 2026-08-25 09:14 | 2026-08-28 | 3 | [2026-08-12 00:14] Sofia Rossi: Performance test results: p95 down from 2.4s to 280ms. [2026-08-13 13:14] Daniel Ortiz: This depends on PROJ-1029 being completed first. [2026-08-14 22:14] Rahul Verma: Is this blocking the release or can it slip to next sprint?
PROJ-1003 | Task | Upgrade dependencies used by chart rendering | Bump libraries used by the Reporting component for chart rendering to latest minor versions to address CVEs flagged by Dependabot. | Done | Fixed | High | Reporting |  | Kenji Tanaka | Chloe Nguyen | Sprint 42 | 13 |  | 2026.09.0 | 2026-08-13 10:18 | 2026-08-20 12:18 | 2026-08-20 12:18 | 2026-09-03 | 3 | [2026-08-14 20:18] Daniel Ortiz: Customer Acme Corp is also asking about this; marking as high visibility. [2026-08-16 23:18] Chloe Nguyen: Rollback performed; issue no longer occurring in prod. [2026-08-17 04:18] Lucas Martin: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1004 | Task | Document CI pipeline runbook | Create an on-call runbook for CI pipeline: dashboards to check, common failure modes, rollback steps and escalation contacts. | Done | Fixed | Medium | Infra |  | Emma Clarke | Rahul Verma | Sprint 42 | 3 | PROJ-1071 | 2026.08.1 | 2026-08-26 17:28 | 2026-08-28 20:28 | 2026-08-28 20:28 | 2026-09-09 | 2 | [2026-08-28 08:28] Rahul Verma: Code review done, left a few minor comments. LGTM otherwise. [2026-08-29 18:28] Emma Clarke: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1005 | Bug | Saved cards shows wrong data for some accounts | Several enterprise customers report that saved cards displays data belonging to the previous billing period. Possibly a timezone issue in the Payments layer. | In Review | Unresolved | Low | Payments | security | Priya Sharma | Aarav Mehta | Sprint 45 | 2 | PROJ-1036 | 2026.08.2 | 2026-07-08 15:46 | 2026-07-14 16:46 |  | 2026-07-22 | 4 | [2026-07-09 08:46] Aarav Mehta: Is this blocking the release or can it slip to next sprint? [2026-07-10 12:46] Priya Sharma: Moved to backlog — lower priority than the Search work this sprint. [2026-07-11 06:46] Aarav Mehta: Design mockups attached. Please review before we start. [2026-07-11 11:46] Lucas Martin: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1006 | Bug | MFA enrollment broken on Safari 17 | MFA enrollment does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | To Do | Unresolved | Highest | Auth |  | Unassigned | Sofia Rossi |  | 8 |  |  | 2026-09-11 12:37 | 2026-09-21 12:37 |  | 2026-10-07 | 3 | [2026-09-12 06:37] Sofia Rossi: PR is up for review: https://git.example.com/auth/pull/371 [2026-09-12 08:37] Sofia Rossi: Design mockups attached. Please review before we start. [2026-09-14 18:37] Sofia Rossi: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1007 | Bug | Refund flow fails intermittently in production | Users report that refund flow fails roughly 1 in 20 attempts. Error logs show a 500 from the Payments service. Steps: 1) Log in 2) Trigger refund flow 3) Observe error toast. Expected: operation succeeds. | Done | Fixed | High | Payments | performance, q4-goal, customer-reported | Sofia Rossi | Kenji Tanaka | Sprint 41 | 1 |  | 2026.09.0 | 2026-08-13 12:43 | 2026-08-24 16:43 | 2026-08-24 16:43 | 2026-09-05 | 3 | [2026-08-13 16:43] Rahul Verma: I can reproduce this on staging. Attaching HAR file. [2026-08-13 18:43] Kenji Tanaka: Discussed in standup — we'll pick this up after the current hotfix. [2026-08-14 23:43] Sofia Rossi: Added more logging, will check again after tomorrow's deploy.
PROJ-1008 | Story | As a user, I want improved log retention | As a user, I want log retention to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | Done | Fixed | Lowest | Infra | performance | Rahul Verma | Daniel Ortiz |  | 2 |  | 2026.08.2 | 2026-07-04 11:47 | 2026-07-19 16:47 | 2026-07-19 16:47 | 2026-07-24 | 1 | [2026-07-05 13:47] Daniel Ortiz: Looping in Lucas Martin since they own this area.
PROJ-1009 | Bug | Redis cache fails intermittently in production | Users report that Redis cache fails roughly 1 in 20 attempts. Error logs show a 500 from the Infra service. Steps: 1) Log in 2) Trigger Redis cache 3) Observe error toast. Expected: operation succeeds. | Won't Do | Won't Fix | High | Infra | customer-reported, hotfix | Rahul Verma | Chloe Nguyen | Sprint 42 | 8 | PROJ-1094 |  | 2026-09-07 14:01 | 2026-09-09 18:01 | 2026-09-09 18:01 | 2026-09-19 | 3 | [2026-09-08 19:01] Chloe Nguyen: Duplicate of PROJ-1006. Closing this one. [2026-09-10 06:01] Priya Sharma: This depends on PROJ-1085 being completed first. [2026-09-12 17:01] Kenji Tanaka: QA verified on staging, looks good.
PROJ-1010 | Story | Add audit logging to in-app inbox | Compliance requires that every action in in-app inbox is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Done | Fixed | Low | Notifications | q4-goal | Kenji Tanaka | Omar Haddad |  | 8 |  |  | 2026-08-21 17:53 | 2026-08-22 21:53 | 2026-08-22 21:53 | 2026-09-06 | 3 | [2026-08-23 00:53] Kenji Tanaka: Design mockups attached. Please review before we start. [2026-08-24 10:53] Omar Haddad: Security team signed off on the approach. [2026-08-24 14:53] Omar Haddad: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1011 | Bug | Database migration broken on Safari 17 | Database migration does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Done | Fixed | Highest | Infra |  | Rahul Verma | Priya Sharma | Sprint 45 | 1 | PROJ-1060 |  | 2026-07-29 11:51 | 2026-08-10 19:51 | 2026-08-10 19:51 | 2026-08-19 | 5 | [2026-07-31 00:51] Rahul Verma: Duplicate of PROJ-1021. Closing this one. [2026-07-31 18:51] Priya Sharma: Code review done, left a few minor comments. LGTM otherwise. [2026-08-01 13:51] Daniel Ortiz: Could not reproduce on latest build. Can the reporter confirm? [2026-08-02 04:51] Rahul Verma: Is this blocking the release or can it slip to next sprint? [2026-08-03 06:51] Rahul Verma: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1012 | Bug | In-app inbox shows wrong data for some accounts | Several enterprise customers report that in-app inbox displays data belonging to the previous billing period. Possibly a timezone issue in the Notifications layer. | In Review | Unresolved | Medium | Notifications | customer-reported | Daniel Ortiz | Rahul Verma | Sprint 41 | 5 | PROJ-1060 | 2026.08.1 | 2026-08-29 11:39 | 2026-09-07 11:39 |  | 2026-09-17 | 2 | [2026-08-29 16:39] Daniel Ortiz: Merged to main. Will be in release 2026.09.1. [2026-08-31 18:39] Priya Sharma: Estimating at 2 story points after refinement.
PROJ-1013 | Task | Document push notifications runbook | Create an on-call runbook for push notifications: dashboards to check, common failure modes, rollback steps and escalation contacts. | To Do | Unresolved | High | Notifications | regression, performance | Sofia Rossi | Priya Sharma | Sprint 43 | 1 |  |  | 2026-08-02 14:10 | 2026-08-12 15:10 |  | 2026-08-14 | 5 | [2026-08-04 11:10] Kenji Tanaka: Root cause identified: cache key did not include tenant id. [2026-08-06 03:10] Chloe Nguyen: Discussed in standup — we'll pick this up after the current hotfix. [2026-08-07 02:10] Sofia Rossi: I can reproduce this on staging. Attaching HAR file. [2026-08-07 15:10] Sofia Rossi: Rollback performed; issue no longer occurring in prod. [2026-08-08 13:10] Sofia Rossi: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1014 | Bug | Slow response time for Elasticsearch index | P95 latency for Elasticsearch index has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Search module. | In Progress | Unresolved | Low | Search | hotfix, performance, regression | Chloe Nguyen | Kenji Tanaka | Sprint 43 | 13 |  |  | 2026-07-02 17:12 | 2026-07-04 20:12 |  | 2026-08-01 | 4 | [2026-07-04 21:12] Chloe Nguyen: I can reproduce this on staging. Attaching HAR file. [2026-07-06 05:12] Chloe Nguyen: This depends on PROJ-1090 being completed first. [2026-07-07 02:12] Chloe Nguyen: Merged to main. Will be in release 2026.08.2. [2026-07-07 15:12] Kenji Tanaka: PR is up for review: https://git.example.com/search/pull/595
PROJ-1015 | Bug | Crash when using filters panel with empty input | Submitting filters panel with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | To Do | Unresolved | Highest | Search | hotfix, security | Unassigned | Aarav Mehta | Sprint 42 | 2 |  |  | 2026-07-17 16:06 | 2026-07-31 16:06 |  | 2026-08-11 | 3 | [2026-07-20 01:06] Daniel Ortiz: Moved to backlog — lower priority than the Auth work this sprint. [2026-07-20 22:06] Aarav Mehta: Is this blocking the release or can it slip to next sprint? [2026-07-23 07:06] Sofia Rossi: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1016 | Bug | PDF report broken on Safari 17 | PDF report does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | To Do | Unresolved | Highest | Reporting | hotfix, customer-reported | Rahul Verma | Aarav Mehta | Sprint 44 | 13 | PROJ-1034 |  | 2026-09-15 16:18 | 2026-09-16 19:18 |  | 2026-10-01 | 5 | [2026-09-17 12:18] Aarav Mehta: PR is up for review: https://git.example.com/reporting/pull/657 [2026-09-18 00:18] Lucas Martin: QA verified on staging, looks good. [2026-09-18 21:18] Rahul Verma: Root cause identified: cache key did not include tenant id. [2026-09-20 22:18] Kenji Tanaka: Could not reproduce on latest build. Can the reporter confirm? [2026-09-21 02:18] Rahul Verma: Customer Stark Industries is also asking about this; marking as high visibility.
PROJ-1017 | Bug | Slow response time for invoice PDF | P95 latency for invoice PDF has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Payments module. | In Progress | Unresolved | High | Payments |  | Emma Clarke | Daniel Ortiz |  | 3 | PROJ-1015 |  | 2026-08-22 16:18 | 2026-09-02 22:18 |  | 2026-09-15 | 4 | [2026-08-25 01:18] Sofia Rossi: Rollback performed; issue no longer occurring in prod. [2026-08-26 02:18] Emma Clarke: Duplicate of PROJ-1071. Closing this one. [2026-08-27 08:18] Daniel Ortiz: Moved to backlog — lower priority than the Search work this sprint. [2026-08-28 21:18] Emma Clarke: Estimating at 8 story points after refinement.
PROJ-1018 | Story | Add audit logging to chart rendering | Compliance requires that every action in chart rendering is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Done | Fixed | Lowest | Reporting | regression | Lucas Martin | Sofia Rossi |  | 3 |  | 2026.08.2 | 2026-09-09 11:24 | 2026-09-13 19:24 | 2026-09-13 19:24 | 2026-10-09 | 4 | [2026-09-10 10:24] Lucas Martin: Rollback performed; issue no longer occurring in prod. [2026-09-11 10:24] Sofia Rossi: Could not reproduce on latest build. Can the reporter confirm? [2026-09-12 12:24] Lucas Martin: Code review done, left a few minor comments. LGTM otherwise. [2026-09-12 16:24] Sofia Rossi: Added more logging, will check again after tomorrow's deploy.
PROJ-1019 | Epic | Infra revamp: CDN config | Umbrella epic for the Q4 initiative to redesign CDN config in the Infra area. Includes discovery, design, implementation and rollout. | In Review | Unresolved | Lowest | Infra | hotfix, q4-goal | Rahul Verma | Emma Clarke | Sprint 43 |  |  |  | 2026-07-11 14:54 | 2026-07-22 22:54 |  | 2026-07-30 | 5 | [2026-07-11 18:54] Priya Sharma: Duplicate of PROJ-1056. Closing this one. [2026-07-13 17:54] Rahul Verma: Discussed in standup — we'll pick this up after the current hotfix. [2026-07-14 17:54] Emma Clarke: Root cause: missing null check when the infra config is not loaded. [2026-07-16 10:54] Rahul Verma: Root cause identified: cache key did not include tenant id. [2026-07-17 04:54] Emma Clarke: Security team signed off on the approach.
PROJ-1020 | Bug | Slow response time for CDN config | P95 latency for CDN config has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Infra module. | To Do | Unresolved | Medium | Infra | performance, customer-reported, hotfix | Unassigned | Lucas Martin | Sprint 43 | 13 |  |  | 2026-09-12 14:36 | 2026-09-17 18:36 |  | 2026-09-19 | 1 | [2026-09-15 02:36] Sofia Rossi: Duplicate of PROJ-1082. Closing this one.
PROJ-1021 | Bug | Pagination fails intermittently in production | Users report that pagination fails roughly 1 in 20 attempts. Error logs show a 500 from the Search service. Steps: 1) Log in 2) Trigger pagination 3) Observe error toast. Expected: operation succeeds. | In Progress | Unresolved | Medium | Search | tech-debt, regression, q4-goal | Emma Clarke | Omar Haddad | Sprint 45 | 3 |  |  | 2026-07-17 10:58 | 2026-07-22 15:58 |  | 2026-08-16 | 3 | [2026-07-19 17:58] Omar Haddad: Customer Umbrella Ltd is also asking about this; marking as high visibility. [2026-07-21 19:58] Omar Haddad: Code review done, left a few minor comments. LGTM otherwise. [2026-07-23 02:58] Aarav Mehta: Root cause: missing null check when the search config is not loaded.
PROJ-1022 | Bug | Image upload fails intermittently in production | Users report that image upload fails roughly 1 in 20 attempts. Error logs show a 500 from the Mobile service. Steps: 1) Log in 2) Trigger image upload 3) Observe error toast. Expected: operation succeeds. | Done | Fixed | Medium | Mobile | customer-reported | Rahul Verma | Kenji Tanaka | Sprint 42 | 8 | PROJ-1059 |  | 2026-07-15 11:02 | 2026-07-16 15:02 | 2026-07-16 15:02 | 2026-08-06 | 3 | [2026-07-17 07:02] Rahul Verma: This depends on PROJ-1063 being completed first. [2026-07-18 02:02] Emma Clarke: Looping in Emma Clarke since they own this area. [2026-07-20 13:02] Priya Sharma: Performance test results: p95 down from 2.4s to 280ms.
PROJ-1023 | Task | Upgrade dependencies used by login | Bump libraries used by the Auth component for login to latest minor versions to address CVEs flagged by Dependabot. | Won't Do | Won't Fix | Low | Auth | customer-reported | Priya Sharma | Sofia Rossi | Sprint 44 | 3 |  |  | 2026-09-09 12:37 | 2026-09-13 15:37 | 2026-09-13 15:37 | 2026-09-26 | 2 | [2026-09-09 22:37] Sofia Rossi: This depends on PROJ-1046 being completed first. [2026-09-10 20:37] Priya Sharma: I can reproduce this on staging. Attaching HAR file.
PROJ-1024 | Story | Add audit logging to image upload | Compliance requires that every action in image upload is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | QA | Unresolved | Lowest | Mobile | q4-goal, ux, customer-reported | Chloe Nguyen | Aarav Mehta | Sprint 41 | 5 |  | 2026.08.1 | 2026-08-08 16:41 | 2026-08-09 16:41 |  | 2026-08-30 | 4 | [2026-08-08 22:41] Omar Haddad: Is this blocking the release or can it slip to next sprint? [2026-08-10 21:41] Priya Sharma: Could not reproduce on latest build. Can the reporter confirm? [2026-08-12 16:41] Chloe Nguyen: This depends on PROJ-1059 being completed first. [2026-08-14 16:41] Aarav Mehta: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1025 | Bug | Slow response time for invoice PDF | P95 latency for invoice PDF has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Payments module. | Done | Fixed | Medium | Payments | customer-reported, tech-debt, performance | Chloe Nguyen | Omar Haddad |  | 3 | PROJ-1074 | 2026.08.1 | 2026-09-10 14:42 | 2026-09-12 20:42 | 2026-09-12 20:42 | 2026-09-28 | 5 | [2026-09-11 05:42] Kenji Tanaka: Added more logging, will check again after tomorrow's deploy. [2026-09-11 21:42] Chloe Nguyen: Estimating at 2 story points after refinement. [2026-09-13 19:42] Daniel Ortiz: QA verified on staging, looks good. [2026-09-15 13:42] Omar Haddad: I can reproduce this on staging. Attaching HAR file. [2026-09-16 14:42] Omar Haddad: QA verified on staging, looks good.
PROJ-1026 | Story | Add audit logging to date range picker | Compliance requires that every action in date range picker is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Done | Fixed | Medium | Reporting | performance, customer-reported, regression | Chloe Nguyen | Sofia Rossi | Sprint 44 | 5 |  |  | 2026-07-15 14:27 | 2026-07-17 18:27 | 2026-07-17 18:27 | 2026-08-12 | 1 | [2026-07-15 16:27] Sofia Rossi: PR is up for review: https://git.example.com/reporting/pull/885
PROJ-1027 | Bug | Crash when using CI pipeline with empty input | Submitting CI pipeline with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | Done | Fixed | Medium | Infra | q4-goal, performance | Priya Sharma | Emma Clarke | Sprint 45 | 13 | PROJ-1015 | 2026.10.0 | 2026-08-20 09:27 | 2026-08-21 16:27 | 2026-08-21 16:27 | 2026-08-29 | 4 | [2026-08-20 12:27] Priya Sharma: Could not reproduce on latest build. Can the reporter confirm? [2026-08-22 03:27] Emma Clarke: Root cause identified: cache key did not include tenant id. [2026-08-23 13:27] Emma Clarke: Performance test results: p95 down from 2.4s to 280ms. [2026-08-23 21:27] Priya Sharma: Added more logging, will check again after tomorrow's deploy.
PROJ-1028 | Task | Document OpenAPI docs runbook | Create an on-call runbook for OpenAPI docs: dashboards to check, common failure modes, rollback steps and escalation contacts. | Done | Fixed | Lowest | API | performance, hotfix | Omar Haddad | Emma Clarke | Sprint 44 | 1 | PROJ-1010 | 2026.09.1 | 2026-07-20 16:04 | 2026-07-28 23:04 | 2026-07-28 23:04 | 2026-08-16 | 3 | [2026-07-21 23:04] Omar Haddad: Design mockups attached. Please review before we start. [2026-07-23 01:04] Omar Haddad: Design mockups attached. Please review before we start. [2026-07-24 11:04] Sofia Rossi: Added more logging, will check again after tomorrow's deploy.
PROJ-1029 | Bug | Slow response time for filters panel | P95 latency for filters panel has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Search module. | In Progress | Unresolved | Low | Search | performance, tech-debt, ux | Aarav Mehta | Omar Haddad | Sprint 43 | 8 |  |  | 2026-09-19 14:04 | 2026-09-25 15:04 |  | 2026-10-13 | 3 | [2026-09-19 21:04] Aarav Mehta: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-09-21 16:04] Omar Haddad: Could not reproduce on latest build. Can the reporter confirm? [2026-09-22 17:04] Omar Haddad: QA verified on staging, looks good.
PROJ-1030 | Task | Document currency conversion runbook | Create an on-call runbook for currency conversion: dashboards to check, common failure modes, rollback steps and escalation contacts. | Blocked | Unresolved | Highest | Payments | hotfix | Daniel Ortiz | Emma Clarke | Sprint 42 | 1 | PROJ-1087 |  | 2026-09-15 15:09 | 2026-09-18 17:09 |  | 2026-10-14 | 2 | [2026-09-16 21:09] Emma Clarke: Duplicate of PROJ-1040. Closing this one. [2026-09-17 22:09] Sofia Rossi: Security team signed off on the approach.
PROJ-1031 | Story | Add audit logging to CSV export | Compliance requires that every action in CSV export is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | QA | Unresolved | High | Reporting | q4-goal | Priya Sharma | Chloe Nguyen |  | 1 |  | 2026.08.2 | 2026-08-06 10:48 | 2026-08-09 14:48 |  | 2026-08-27 | 2 | [2026-08-08 16:48] Chloe Nguyen: Design mockups attached. Please review before we start. [2026-08-09 17:48] Priya Sharma: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1032 | Story | As a user, I want improved API key rotation | As a user, I want API key rotation to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | To Do | Unresolved | High | API | regression, customer-reported | Chloe Nguyen | Daniel Ortiz | Sprint 43 | 2 | PROJ-1080 |  | 2026-09-16 17:27 | 2026-09-18 21:27 |  | 2026-09-30 | 4 | [2026-09-16 23:27] Daniel Ortiz: Discussed in standup — we'll pick this up after the current hotfix. [2026-09-18 16:27] Chloe Nguyen: Root cause: missing null check when the api config is not loaded. [2026-09-20 02:27] Kenji Tanaka: Rollback performed; issue no longer occurring in prod. [2026-09-20 05:27] Emma Clarke: Root cause: missing null check when the api config is not loaded.
PROJ-1033 | Story | Support localisation for pagination | Pagination must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | In Review | Unresolved | High | Search |  | Priya Sharma | Daniel Ortiz |  | 3 |  |  | 2026-08-28 09:18 | 2026-09-01 09:18 |  | 2026-09-10 | 5 | [2026-08-29 12:18] Aarav Mehta: This depends on PROJ-1100 being completed first. [2026-08-30 11:18] Priya Sharma: Merged to main. Will be in release 2026.09.1. [2026-09-01 09:18] Daniel Ortiz: Moved to backlog — lower priority than the Payments work this sprint. [2026-09-02 21:18] Omar Haddad: QA verified on staging, looks good. [2026-09-04 02:18] Daniel Ortiz: Customer Initech is also asking about this; marking as high visibility.
PROJ-1034 | Story | Support localisation for Redis cache | Redis cache must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | Done | Fixed | Lowest | Infra | customer-reported, performance, regression | Lucas Martin | Daniel Ortiz | Sprint 42 | 13 | PROJ-1048 |  | 2026-07-05 11:04 | 2026-07-09 16:04 | 2026-07-09 16:04 | 2026-07-23 | 3 | [2026-07-06 17:04] Daniel Ortiz: Is this blocking the release or can it slip to next sprint? [2026-07-07 02:04] Kenji Tanaka: I can reproduce this on staging. Attaching HAR file. [2026-07-08 08:04] Lucas Martin: PR is up for review: https://git.example.com/infra/pull/810
PROJ-1035 | Task | Write integration tests for rate limiting | Coverage for rate limiting is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | Done | Fixed | Medium | API | regression | Omar Haddad | Chloe Nguyen | Sprint 43 | 2 |  |  | 2026-08-07 13:54 | 2026-08-10 15:54 | 2026-08-10 15:54 | 2026-08-25 | 2 | [2026-08-09 17:54] Daniel Ortiz: Moved to backlog — lower priority than the API work this sprint. [2026-08-12 03:54] Chloe Nguyen: Is this blocking the release or can it slip to next sprint?
PROJ-1036 | Story | Support localisation for invoice PDF | Invoice PDF must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | In Progress | Unresolved | Low | Payments | performance | Daniel Ortiz | Chloe Nguyen | Sprint 45 | 2 | PROJ-1091 |  | 2026-07-17 15:32 | 2026-08-01 15:32 |  | 2026-07-27 | 2 | [2026-07-18 15:32] Kenji Tanaka: Rollback performed; issue no longer occurring in prod. [2026-07-20 03:32] Omar Haddad: Is this blocking the release or can it slip to next sprint?
PROJ-1037 | Bug | Image upload fails intermittently in production | Users report that image upload fails roughly 1 in 20 attempts. Error logs show a 500 from the Mobile service. Steps: 1) Log in 2) Trigger image upload 3) Observe error toast. Expected: operation succeeds. | To Do | Unresolved | Lowest | Mobile | performance, security, customer-reported | Kenji Tanaka | Omar Haddad | Sprint 43 | 13 | PROJ-1059 |  | 2026-09-12 15:39 | 2026-09-23 15:39 |  | 2026-10-04 | 1 | [2026-09-14 13:39] Omar Haddad: Looping in Daniel Ortiz since they own this area.
PROJ-1038 | Epic | Mobile revamp: biometric login | Umbrella epic for the Q4 initiative to redesign biometric login in the Mobile area. Includes discovery, design, implementation and rollout. | Won't Do | Won't Fix | High | Mobile | hotfix, regression | Chloe Nguyen | Emma Clarke | Sprint 41 |  |  |  | 2026-09-10 10:20 | 2026-09-14 17:20 | 2026-09-14 17:20 | 2026-09-20 | 2 | [2026-09-10 18:20] Emma Clarke: Looping in Kenji Tanaka since they own this area. [2026-09-12 18:20] Emma Clarke: Could not reproduce on latest build. Can the reporter confirm?
PROJ-1039 | Story | As a user, I want improved log retention | As a user, I want log retention to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Progress | Unresolved | Medium | Infra | tech-debt, hotfix, ux | Kenji Tanaka | Aarav Mehta | Sprint 41 | 3 |  |  | 2026-09-02 16:18 | 2026-09-11 16:18 |  | 2026-09-12 | 3 | [2026-09-02 20:18] Rahul Verma: Root cause identified: cache key did not include tenant id. [2026-09-04 02:18] Kenji Tanaka: This depends on PROJ-1013 being completed first. [2026-09-06 06:18] Aarav Mehta: Could not reproduce on latest build. Can the reporter confirm?
PROJ-1040 | Bug | Pagination shows wrong data for some accounts | Several enterprise customers report that pagination displays data belonging to the previous billing period. Possibly a timezone issue in the Search layer. | QA | Unresolved | High | Search | hotfix, ux | Daniel Ortiz | Chloe Nguyen | Sprint 45 | 5 |  | 2026.10.0 | 2026-08-11 14:10 | 2026-08-18 18:10 |  | 2026-09-05 | 3 | [2026-08-12 13:10] Omar Haddad: Security team signed off on the approach. [2026-08-13 05:10] Chloe Nguyen: Looping in Omar Haddad since they own this area. [2026-08-14 19:10] Daniel Ortiz: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1041 | Story | Support localisation for OpenAPI docs | OpenAPI docs must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | To Do | Unresolved | High | API | performance, hotfix | Lucas Martin | Emma Clarke | Sprint 45 | 5 | PROJ-1032 |  | 2026-08-10 11:29 | 2026-08-25 19:29 |  | 2026-08-27 | 3 | [2026-08-12 00:29] Lucas Martin: QA verified on staging, looks good. [2026-08-13 13:29] Lucas Martin: Merged to main. Will be in release 2026.10.0. [2026-08-13 17:29] Lucas Martin: QA verified on staging, looks good.
PROJ-1042 | Bug | Crash when using dashboard widgets with empty input | Submitting dashboard widgets with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | In Progress | Unresolved | Highest | Reporting | regression, ux, hotfix, customer-reported | Sofia Rossi | Chloe Nguyen | Sprint 44 | 8 |  |  | 2026-07-30 09:06 | 2026-08-06 14:06 |  | 2026-08-28 | 2 | [2026-07-31 13:06] Chloe Nguyen: Performance test results: p95 down from 2.4s to 280ms. [2026-08-02 08:06] Sofia Rossi: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1043 | Epic | Search revamp: pagination | Umbrella epic for the Q4 initiative to redesign pagination in the Search area. Includes discovery, design, implementation and rollout. | Done | Fixed | Highest | Search | tech-debt, q4-goal, performance | Priya Sharma | Omar Haddad | Sprint 42 |  |  | 2026.08.1 | 2026-08-12 13:29 | 2026-08-23 21:29 | 2026-08-23 21:29 | 2026-09-04 | 4 | [2026-08-13 08:29] Priya Sharma: PR is up for review: https://git.example.com/search/pull/266 [2026-08-14 22:29] Rahul Verma: Security team signed off on the approach. [2026-08-15 06:29] Priya Sharma: Customer Umbrella Ltd is also asking about this; marking as high visibility. [2026-08-17 08:29] Emma Clarke: Merged to main. Will be in release 2026.10.0.
PROJ-1044 | Bug | Invoice PDF shows wrong data for some accounts | Several enterprise customers report that invoice PDF displays data belonging to the previous billing period. Possibly a timezone issue in the Payments layer. | Done | Fixed | Low | Payments | tech-debt, security, ux | Priya Sharma | Kenji Tanaka | Sprint 43 | 3 | PROJ-1071 | 2026.08.1 | 2026-08-07 14:39 | 2026-08-11 17:39 | 2026-08-11 17:39 | 2026-08-18 | 4 | [2026-08-09 16:39] Kenji Tanaka: This depends on PROJ-1068 being completed first. [2026-08-12 04:39] Emma Clarke: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-08-13 10:39] Kenji Tanaka: Discussed in standup — we'll pick this up after the current hotfix. [2026-08-14 20:39] Priya Sharma: Estimating at 8 story points after refinement.
PROJ-1045 | Bug | Unsubscribe link shows wrong data for some accounts | Several enterprise customers report that unsubscribe link displays data belonging to the previous billing period. Possibly a timezone issue in the Notifications layer. | In Progress | Unresolved | Highest | Notifications | ux, security, q4-goal | Priya Sharma | Aarav Mehta | Sprint 45 | 5 | PROJ-1088 |  | 2026-08-30 09:18 | 2026-09-06 11:18 |  | 2026-09-10 | 5 | [2026-08-30 19:18] Aarav Mehta: Performance test results: p95 down from 2.4s to 280ms. [2026-09-01 21:18] Priya Sharma: I can reproduce this on staging. Attaching HAR file. [2026-09-02 21:18] Aarav Mehta: Added more logging, will check again after tomorrow's deploy. [2026-09-03 12:18] Priya Sharma: Is this blocking the release or can it slip to next sprint? [2026-09-04 18:18] Priya Sharma: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1046 | Bug | Android deep links broken on Safari 17 | Android deep links does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Won't Do | Won't Fix | Medium | Mobile | hotfix, customer-reported, tech-debt | Kenji Tanaka | Rahul Verma | Sprint 42 | 13 |  |  | 2026-08-05 09:35 | 2026-08-15 11:35 | 2026-08-15 11:35 | 2026-09-01 | 5 | [2026-08-06 07:35] Kenji Tanaka: Estimating at 3 story points after refinement. [2026-08-08 15:35] Kenji Tanaka: Added more logging, will check again after tomorrow's deploy. [2026-08-09 06:35] Kenji Tanaka: Could not reproduce on latest build. Can the reporter confirm? [2026-08-11 03:35] Kenji Tanaka: Duplicate of PROJ-1062. Closing this one. [2026-08-12 00:35] Omar Haddad: I can reproduce this on staging. Attaching HAR file.
PROJ-1047 | Story | Add audit logging to CI pipeline | Compliance requires that every action in CI pipeline is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | In Progress | Unresolved | Medium | Infra |  | Kenji Tanaka | Emma Clarke | Sprint 45 | 13 | PROJ-1041 |  | 2026-08-03 14:32 | 2026-08-18 21:32 |  | 2026-08-24 | 2 | [2026-08-04 15:32] Chloe Nguyen: Could not reproduce on latest build. Can the reporter confirm? [2026-08-06 06:32] Kenji Tanaka: Estimating at 3 story points after refinement.
PROJ-1048 | Task | Write integration tests for offline mode | Coverage for offline mode is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | Won't Do | Won't Fix | Medium | Mobile | customer-reported | Omar Haddad | Lucas Martin | Sprint 44 | 8 | PROJ-1010 |  | 2026-07-22 14:10 | 2026-07-25 22:10 | 2026-07-25 22:10 | 2026-08-13 | 1 | [2026-07-24 16:10] Sofia Rossi: I can reproduce this on staging. Attaching HAR file.
PROJ-1049 | Story | Support localisation for iOS app launch | IOS app launch must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | Blocked | Unresolved | Low | Mobile | performance, customer-reported | Aarav Mehta | Lucas Martin | Sprint 41 | 8 |  |  | 2026-07-01 17:35 | 2026-07-08 17:35 |  | 2026-07-08 | 4 | [2026-07-03 22:35] Aarav Mehta: Customer Acme Corp is also asking about this; marking as high visibility. [2026-07-06 04:35] Sofia Rossi: Root cause: missing null check when the mobile config is not loaded. [2026-07-06 20:35] Rahul Verma: QA verified on staging, looks good. [2026-07-08 04:35] Emma Clarke: Looping in Aarav Mehta since they own this area.
PROJ-1050 | Bug | Crash when using SSO with empty input | Submitting SSO with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | In Review | Unresolved | Highest | Auth | tech-debt | Kenji Tanaka | Priya Sharma |  | 13 |  | 2026.08.1 | 2026-09-08 09:11 | 2026-09-23 14:11 |  | 2026-09-15 | 1 | [2026-09-09 06:11] Daniel Ortiz: Customer Globex is also asking about this; marking as high visibility.
PROJ-1051 | Bug | IOS app launch broken on Safari 17 | IOS app launch does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Done | Fixed | Medium | Mobile | ux | Rahul Verma | Omar Haddad | Sprint 43 | 5 | PROJ-1088 | 2026.09.0 | 2026-08-11 09:40 | 2026-08-16 16:40 | 2026-08-16 16:40 | 2026-09-02 | 5 | [2026-08-13 05:40] Rahul Verma: Root cause identified: cache key did not include tenant id. [2026-08-15 04:40] Rahul Verma: Performance test results: p95 down from 2.4s to 280ms. [2026-08-16 10:40] Chloe Nguyen: Root cause: missing null check when the mobile config is not loaded. [2026-08-17 20:40] Rahul Verma: Estimating at 2 story points after refinement. [2026-08-19 00:40] Rahul Verma: Root cause identified: cache key did not include tenant id.
PROJ-1052 | Bug | V2 orders endpoint shows wrong data for some accounts | Several enterprise customers report that v2 orders endpoint displays data belonging to the previous billing period. Possibly a timezone issue in the API layer. | In Progress | Unresolved | High | API | hotfix, customer-reported | Emma Clarke | Priya Sharma | Sprint 45 | 3 | PROJ-1051 |  | 2026-08-02 12:46 | 2026-08-13 19:46 |  | 2026-08-28 | 3 | [2026-08-04 19:46] Emma Clarke: Duplicate of PROJ-1039. Closing this one. [2026-08-06 17:46] Lucas Martin: PR is up for review: https://git.example.com/api/pull/281 [2026-08-08 21:46] Sofia Rossi: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1053 | Task | Upgrade dependencies used by pagination | Bump libraries used by the Search component for pagination to latest minor versions to address CVEs flagged by Dependabot. | Won't Do | Won't Fix | Medium | Search | tech-debt, ux, hotfix | Lucas Martin | Sofia Rossi |  | 2 | PROJ-1020 |  | 2026-08-07 10:52 | 2026-08-21 16:52 | 2026-08-21 16:52 | 2026-09-04 | 4 | [2026-08-09 14:52] Lucas Martin: Root cause identified: cache key did not include tenant id. [2026-08-11 12:52] Sofia Rossi: This depends on PROJ-1022 being completed first. [2026-08-13 02:52] Sofia Rossi: Performance test results: p95 down from 2.4s to 280ms. [2026-08-14 12:52] Lucas Martin: Rollback performed; issue no longer occurring in prod.
PROJ-1054 | Epic | Search revamp: filters panel | Umbrella epic for the Q4 initiative to redesign filters panel in the Search area. Includes discovery, design, implementation and rollout. | To Do | Unresolved | Medium | Search | ux, security, customer-reported | Omar Haddad | Priya Sharma | Sprint 41 |  |  |  | 2026-07-19 14:19 | 2026-07-25 21:19 |  | 2026-08-01 | 4 | [2026-07-21 14:19] Priya Sharma: Design mockups attached. Please review before we start. [2026-07-23 19:19] Omar Haddad: Customer Stark Industries is also asking about this; marking as high visibility. [2026-07-24 11:19] Priya Sharma: Root cause identified: cache key did not include tenant id. [2026-07-25 17:19] Priya Sharma: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1055 | Bug | Filters panel shows wrong data for some accounts | Several enterprise customers report that filters panel displays data belonging to the previous billing period. Possibly a timezone issue in the Search layer. | To Do | Unresolved | Medium | Search | hotfix, performance, customer-reported | Chloe Nguyen | Lucas Martin | Sprint 45 | 13 |  |  | 2026-08-10 15:39 | 2026-08-17 16:39 |  | 2026-08-28 | 3 | [2026-08-13 03:39] Lucas Martin: Duplicate of PROJ-1031. Closing this one. [2026-08-13 16:39] Chloe Nguyen: Root cause: missing null check when the search config is not loaded. [2026-08-15 10:39] Chloe Nguyen: This depends on PROJ-1024 being completed first.
PROJ-1056 | Epic | Auth revamp: password reset | Umbrella epic for the Q4 initiative to redesign password reset in the Auth area. Includes discovery, design, implementation and rollout. | To Do | Unresolved | Low | Auth | regression | Omar Haddad | Chloe Nguyen | Sprint 45 |  |  |  | 2026-08-22 16:26 | 2026-09-03 23:26 |  | 2026-09-13 | 5 | [2026-08-22 19:26] Lucas Martin: Code review done, left a few minor comments. LGTM otherwise. [2026-08-24 20:26] Omar Haddad: Moved to backlog — lower priority than the Reporting work this sprint. [2026-08-26 08:26] Omar Haddad: Looping in Lucas Martin since they own this area. [2026-08-27 02:26] Omar Haddad: Root cause: missing null check when the auth config is not loaded. [2026-08-28 02:26] Omar Haddad: Duplicate of PROJ-1008. Closing this one.
PROJ-1057 | Story | Add audit logging to chart rendering | Compliance requires that every action in chart rendering is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Won't Do | Won't Fix | High | Reporting | tech-debt, ux | Kenji Tanaka | Omar Haddad | Sprint 44 | 2 | PROJ-1092 |  | 2026-09-04 10:08 | 2026-09-17 16:08 | 2026-09-17 16:08 | 2026-09-12 | 3 | [2026-09-06 17:08] Omar Haddad: Code review done, left a few minor comments. LGTM otherwise. [2026-09-08 11:08] Emma Clarke: Is this blocking the release or can it slip to next sprint? [2026-09-08 13:08] Omar Haddad: Is this blocking the release or can it slip to next sprint?
PROJ-1058 | Task | Write integration tests for scheduled reports | Coverage for scheduled reports is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | QA | Unresolved | High | Reporting |  | Emma Clarke | Lucas Martin | Sprint 41 | 2 | PROJ-1001 | 2026.08.1 | 2026-07-07 09:06 | 2026-07-18 16:06 |  | 2026-07-14 | 4 | [2026-07-07 23:06] Emma Clarke: Added more logging, will check again after tomorrow's deploy. [2026-07-09 19:06] Priya Sharma: Performance test results: p95 down from 2.4s to 280ms. [2026-07-10 03:06] Aarav Mehta: I can reproduce this on staging. Attaching HAR file. [2026-07-11 02:06] Priya Sharma: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1059 | Task | Upgrade dependencies used by offline mode | Bump libraries used by the Mobile component for offline mode to latest minor versions to address CVEs flagged by Dependabot. | In Progress | Unresolved | Low | Mobile | security, ux | Omar Haddad | Daniel Ortiz | Sprint 41 | 13 | PROJ-1053 |  | 2026-07-09 17:36 | 2026-07-10 19:36 |  | 2026-07-30 | 5 | [2026-07-11 14:36] Omar Haddad: Design mockups attached. Please review before we start. [2026-07-13 18:36] Aarav Mehta: Added more logging, will check again after tomorrow's deploy. [2026-07-16 04:36] Daniel Ortiz: QA verified on staging, looks good. [2026-07-17 13:36] Daniel Ortiz: Root cause identified: cache key did not include tenant id. [2026-07-18 15:36] Daniel Ortiz: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1060 | Bug | Dashboard widgets fails intermittently in production | Users report that dashboard widgets fails roughly 1 in 20 attempts. Error logs show a 500 from the Reporting service. Steps: 1) Log in 2) Trigger dashboard widgets 3) Observe error toast. Expected: operation succeeds. | Blocked | Unresolved | Medium | Reporting | performance, customer-reported | Chloe Nguyen | Kenji Tanaka | Sprint 43 | 1 |  |  | 2026-08-23 15:44 | 2026-08-30 16:44 |  | 2026-09-19 | 2 | [2026-08-25 20:44] Rahul Verma: Added more logging, will check again after tomorrow's deploy. [2026-08-28 04:44] Kenji Tanaka: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1061 | Bug | Autocomplete broken on Safari 17 | Autocomplete does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Done | Fixed | High | Search | regression, q4-goal | Chloe Nguyen | Emma Clarke |  | 3 |  |  | 2026-09-05 13:10 | 2026-09-11 15:10 | 2026-09-11 15:10 | 2026-10-05 | 3 | [2026-09-07 00:10] Emma Clarke: Is this blocking the release or can it slip to next sprint? [2026-09-08 09:10] Emma Clarke: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-09-08 13:10] Aarav Mehta: I can reproduce this on staging. Attaching HAR file.
PROJ-1062 | Bug | CI pipeline shows wrong data for some accounts | Several enterprise customers report that CI pipeline displays data belonging to the previous billing period. Possibly a timezone issue in the Infra layer. | Blocked | Unresolved | High | Infra | customer-reported | Emma Clarke | Priya Sharma | Sprint 44 | 5 | PROJ-1060 |  | 2026-07-16 17:43 | 2026-07-31 17:43 |  | 2026-07-28 | 3 | [2026-07-18 20:43] Kenji Tanaka: QA verified on staging, looks good. [2026-07-21 00:43] Priya Sharma: QA verified on staging, looks good. [2026-07-21 11:43] Aarav Mehta: I can reproduce this on staging. Attaching HAR file.
PROJ-1063 | Bug | CSV export broken on Safari 17 | CSV export does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | In Review | Unresolved | Lowest | Reporting | hotfix, ux, customer-reported | Kenji Tanaka | Daniel Ortiz |  | 1 |  | 2026.10.0 | 2026-07-12 09:58 | 2026-07-16 17:58 |  | 2026-08-01 | 4 | [2026-07-12 15:58] Kenji Tanaka: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-07-14 13:58] Daniel Ortiz: Could not reproduce on latest build. Can the reporter confirm? [2026-07-15 00:58] Daniel Ortiz: Discussed in standup — we'll pick this up after the current hotfix. [2026-07-16 06:58] Kenji Tanaka: QA verified on staging, looks good.
PROJ-1064 | Task | Write integration tests for SSO | Coverage for SSO is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | To Do | Unresolved | Medium | Auth | security, customer-reported, hotfix | Rahul Verma | Emma Clarke | Sprint 41 | 1 |  |  | 2026-08-08 13:52 | 2026-08-11 13:52 |  | 2026-08-27 | 2 | [2026-08-08 22:52] Priya Sharma: I can reproduce this on staging. Attaching HAR file. [2026-08-10 13:52] Emma Clarke: Merged to main. Will be in release 2026.08.2.
PROJ-1065 | Bug | Crash when using rate limiting with empty input | Submitting rate limiting with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | In Review | Unresolved | Medium | API | performance, security | Aarav Mehta | Lucas Martin | Sprint 42 | 1 |  | 2026.10.0 | 2026-08-18 15:11 | 2026-08-24 18:11 |  | 2026-08-30 | 5 | [2026-08-19 08:11] Aarav Mehta: Performance test results: p95 down from 2.4s to 280ms. [2026-08-19 18:11] Aarav Mehta: Estimating at 3 story points after refinement. [2026-08-21 06:11] Aarav Mehta: Moved to backlog — lower priority than the Reporting work this sprint. [2026-08-22 22:11] Lucas Martin: Code review done, left a few minor comments. LGTM otherwise. [2026-08-24 18:11] Lucas Martin: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1066 | Story | Support localisation for biometric login | Biometric login must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | To Do | Unresolved | Medium | Mobile |  | Daniel Ortiz | Omar Haddad |  | 1 | PROJ-1078 |  | 2026-07-25 16:34 | 2026-07-30 18:34 |  | 2026-08-16 | 2 | [2026-07-25 19:34] Daniel Ortiz: Rollback performed; issue no longer occurring in prod. [2026-07-26 00:34] Emma Clarke: I can reproduce this on staging. Attaching HAR file.
PROJ-1067 | Bug | Slow response time for log retention | P95 latency for log retention has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Infra module. | In Progress | Unresolved | Lowest | Infra | q4-goal | Lucas Martin | Rahul Verma | Sprint 44 | 13 | PROJ-1023 |  | 2026-08-10 11:45 | 2026-08-19 16:45 |  | 2026-08-24 | 1 | [2026-08-12 09:45] Rahul Verma: Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1068 | Story | As a user, I want improved filters panel | As a user, I want filters panel to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Progress | Unresolved | High | Search |  | Emma Clarke | Priya Sharma | Sprint 44 | 3 | PROJ-1014 |  | 2026-08-27 09:16 | 2026-08-31 12:16 |  | 2026-09-25 | 1 | [2026-08-27 14:16] Emma Clarke: Root cause identified: cache key did not include tenant id.
PROJ-1069 | Task | Document invoice PDF runbook | Create an on-call runbook for invoice PDF: dashboards to check, common failure modes, rollback steps and escalation contacts. | Done | Fixed | Medium | Payments |  | Lucas Martin | Daniel Ortiz |  | 1 | PROJ-1049 | 2026.10.0 | 2026-07-10 09:18 | 2026-07-11 14:18 | 2026-07-11 14:18 | 2026-07-25 | 2 | [2026-07-12 09:18] Daniel Ortiz: Is this blocking the release or can it slip to next sprint? [2026-07-14 19:18] Chloe Nguyen: Estimating at 3 story points after refinement.
PROJ-1070 | Bug | PDF report broken on Safari 17 | PDF report does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | To Do | Unresolved | Medium | Reporting | security, customer-reported, q4-goal | Unassigned | Chloe Nguyen | Sprint 42 | 2 | PROJ-1038 |  | 2026-08-16 09:27 | 2026-08-18 13:27 |  | 2026-09-13 | 1 | [2026-08-17 17:27] Chloe Nguyen: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1071 | Bug | Dark mode shows wrong data for some accounts | Several enterprise customers report that dark mode displays data belonging to the previous billing period. Possibly a timezone issue in the Mobile layer. | To Do | Unresolved | Medium | Mobile | q4-goal, hotfix | Sofia Rossi | Kenji Tanaka | Sprint 45 | 8 | PROJ-1050 |  | 2026-09-11 09:09 | 2026-09-24 10:09 |  | 2026-09-20 | 5 | [2026-09-12 13:09] Aarav Mehta: This depends on PROJ-1051 being completed first. [2026-09-14 03:09] Kenji Tanaka: Rollback performed; issue no longer occurring in prod. [2026-09-16 08:09] Daniel Ortiz: PR is up for review: https://git.example.com/mobile/pull/533 [2026-09-17 02:09] Sofia Rossi: Could not reproduce on latest build. Can the reporter confirm? [2026-09-19 14:09] Daniel Ortiz: I can reproduce this on staging. Attaching HAR file.
PROJ-1072 | Story | As a user, I want improved checkout | As a user, I want checkout to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | Done | Fixed | Low | Payments | performance | Rahul Verma | Emma Clarke | Sprint 42 | 5 | PROJ-1078 | 2026.10.0 | 2026-08-03 15:41 | 2026-08-11 22:41 | 2026-08-11 22:41 | 2026-08-11 | 4 | [2026-08-03 19:41] Rahul Verma: Root cause identified: cache key did not include tenant id. [2026-08-06 01:41] Kenji Tanaka: QA verified on staging, looks good. [2026-08-07 07:41] Rahul Verma: Could not reproduce on latest build. Can the reporter confirm? [2026-08-09 08:41] Rahul Verma: Moved to backlog — lower priority than the Payments work this sprint.
PROJ-1073 | Bug | SSO broken on Safari 17 | SSO does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Done | Fixed | High | Auth | regression, ux, customer-reported | Aarav Mehta | Lucas Martin | Sprint 43 | 2 | PROJ-1077 | 2026.08.2 | 2026-08-16 12:17 | 2026-08-22 19:17 | 2026-08-22 19:17 | 2026-09-08 | 4 | [2026-08-17 01:17] Aarav Mehta: Moved to backlog — lower priority than the Reporting work this sprint. [2026-08-17 04:17] Sofia Rossi: Root cause identified: cache key did not include tenant id. [2026-08-17 19:17] Daniel Ortiz: Merged to main. Will be in release 2026.08.1. [2026-08-20 00:17] Aarav Mehta: I can reproduce this on staging. Attaching HAR file.
PROJ-1074 | Story | Support localisation for GraphQL schema | GraphQL schema must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | In Progress | Unresolved | High | API |  | Emma Clarke | Chloe Nguyen | Sprint 45 | 3 |  |  | 2026-09-10 13:19 | 2026-09-21 14:19 |  | 2026-10-02 | 3 | [2026-09-12 22:19] Chloe Nguyen: Merged to main. Will be in release 2026.09.0. [2026-09-15 03:19] Emma Clarke: Duplicate of PROJ-1038. Closing this one. [2026-09-16 06:19] Sofia Rossi: Root cause identified: cache key did not include tenant id.
PROJ-1075 | Bug | Slow response time for OpenAPI docs | P95 latency for OpenAPI docs has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the API module. | Done | Fixed | Low | API | ux | Daniel Ortiz | Chloe Nguyen | Sprint 44 | 2 | PROJ-1096 | 2026.09.0 | 2026-08-07 10:30 | 2026-08-10 14:30 | 2026-08-10 14:30 | 2026-09-06 | 3 | [2026-08-08 14:30] Aarav Mehta: Could not reproduce on latest build. Can the reporter confirm? [2026-08-10 05:30] Daniel Ortiz: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-08-10 10:30] Chloe Nguyen: Added more logging, will check again after tomorrow's deploy.
PROJ-1076 | Story | As a user, I want improved filters panel | As a user, I want filters panel to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Review | Unresolved | High | Search | q4-goal, security, hotfix | Omar Haddad | Daniel Ortiz | Sprint 45 | 5 | PROJ-1069 | 2026.09.0 | 2026-09-01 10:08 | 2026-09-11 16:08 |  | 2026-09-28 | 2 | [2026-09-03 10:08] Aarav Mehta: Root cause: missing null check when the search config is not loaded. [2026-09-05 10:08] Rahul Verma: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1077 | Task | Write integration tests for autocomplete | Coverage for autocomplete is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | Blocked | Unresolved | Medium | Search | ux, q4-goal, regression | Omar Haddad | Chloe Nguyen | Sprint 45 | 2 |  |  | 2026-08-13 15:56 | 2026-08-24 17:56 |  | 2026-08-30 | 4 | [2026-08-13 18:56] Emma Clarke: Code review done, left a few minor comments. LGTM otherwise. [2026-08-15 13:56] Priya Sharma: Looping in Rahul Verma since they own this area. [2026-08-17 20:56] Omar Haddad: I can reproduce this on staging. Attaching HAR file. [2026-08-19 04:56] Priya Sharma: Added more logging, will check again after tomorrow's deploy.
PROJ-1078 | Story | As a user, I want improved chart rendering | As a user, I want chart rendering to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Review | Unresolved | Low | Reporting | performance | Priya Sharma | Chloe Nguyen | Sprint 42 | 8 |  | 2026.08.1 | 2026-08-06 10:50 | 2026-08-08 17:50 |  | 2026-08-19 | 3 | [2026-08-08 09:50] Priya Sharma: Estimating at 8 story points after refinement. [2026-08-09 02:50] Chloe Nguyen: I can reproduce this on staging. Attaching HAR file. [2026-08-11 02:50] Chloe Nguyen: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1079 | Task | Write integration tests for scheduled reports | Coverage for scheduled reports is at 41%. Add integration tests covering happy path, auth failures and timeouts. Target 80%. | In Review | Unresolved | High | Reporting | regression, tech-debt | Omar Haddad | Aarav Mehta |  | 3 | PROJ-1052 | 2026.10.0 | 2026-07-18 11:21 | 2026-07-24 18:21 |  | 2026-08-13 | 4 | [2026-07-19 18:21] Daniel Ortiz: Merged to main. Will be in release 2026.09.1. [2026-07-21 18:21] Omar Haddad: Looping in Daniel Ortiz since they own this area. [2026-07-23 21:21] Omar Haddad: Root cause: missing null check when the reporting config is not loaded. [2026-07-24 01:21] Chloe Nguyen: Is this blocking the release or can it slip to next sprint?
PROJ-1080 | Story | As a user, I want improved invoice PDF | As a user, I want invoice PDF to be faster and more intuitive so that I can complete my tasks without contacting support. Acceptance criteria: new UI per Figma, analytics events added, feature-flagged rollout. | In Review | Unresolved | Medium | Payments | hotfix, q4-goal, regression | Daniel Ortiz | Rahul Verma | Sprint 43 | 1 |  | 2026.10.0 | 2026-09-10 09:00 | 2026-09-21 11:00 |  | 2026-10-03 | 3 | [2026-09-11 02:00] Daniel Ortiz: Could not reproduce on latest build. Can the reporter confirm? [2026-09-12 08:00] Lucas Martin: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-09-14 03:00] Omar Haddad: I can reproduce this on staging. Attaching HAR file.
PROJ-1081 | Story | Add audit logging to Slack integration | Compliance requires that every action in Slack integration is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | In Progress | Unresolved | Highest | Notifications | hotfix, customer-reported | Lucas Martin | Sofia Rossi | Sprint 42 | 1 |  |  | 2026-08-12 17:49 | 2026-08-23 00:49 |  | 2026-09-10 | 2 | [2026-08-12 19:49] Lucas Martin: Could not reproduce on latest build. Can the reporter confirm? [2026-08-13 05:49] Lucas Martin: Estimating at 3 story points after refinement.
PROJ-1082 | Task | Upgrade dependencies used by iOS app launch | Bump libraries used by the Mobile component for iOS app launch to latest minor versions to address CVEs flagged by Dependabot. | Blocked | Unresolved | Low | Mobile | customer-reported, performance, ux | Priya Sharma | Omar Haddad | Sprint 45 | 1 |  |  | 2026-08-27 16:42 | 2026-09-07 00:42 |  | 2026-09-07 | 4 | [2026-08-29 23:42] Rahul Verma: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-08-31 15:42] Priya Sharma: Duplicate of PROJ-1051. Closing this one. [2026-09-01 21:42] Chloe Nguyen: Added more logging, will check again after tomorrow's deploy. [2026-09-02 12:42] Daniel Ortiz: PR is up for review: https://git.example.com/mobile/pull/831
PROJ-1083 | Bug | Slow response time for biometric login | P95 latency for biometric login has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Mobile module. | QA | Unresolved | Medium | Mobile |  | Chloe Nguyen | Rahul Verma | Sprint 43 | 1 |  |  | 2026-08-06 15:51 | 2026-08-07 23:51 |  | 2026-08-16 | 2 | [2026-08-07 10:51] Rahul Verma: Customer Wayne Enterprises is also asking about this; marking as high visibility. [2026-08-08 10:51] Chloe Nguyen: Design mockups attached. Please review before we start.
PROJ-1084 | Bug | Slow response time for OAuth token refresh | P95 latency for OAuth token refresh has increased from 300ms to 2.4s since the last release. Suspect an N+1 query in the Auth module. | Won't Do | Won't Fix | Highest | Auth | security, customer-reported | Sofia Rossi | Kenji Tanaka | Sprint 42 | 2 |  |  | 2026-09-18 16:53 | 2026-09-22 21:53 | 2026-09-22 21:53 | 2026-10-13 | 1 | [2026-09-19 05:53] Kenji Tanaka: Customer Acme Corp is also asking about this; marking as high visibility.
PROJ-1085 | Bug | CSV export broken on Safari 17 | CSV export does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | To Do | Unresolved | Low | Reporting |  | Aarav Mehta | Omar Haddad | Sprint 42 | 3 |  |  | 2026-09-19 13:31 | 2026-10-02 21:31 |  | 2026-10-07 | 2 | [2026-09-21 00:31] Omar Haddad: Is this blocking the release or can it slip to next sprint? [2026-09-22 20:31] Aarav Mehta: Could not reproduce on latest build. Can the reporter confirm?
PROJ-1086 | Story | Add audit logging to email digest | Compliance requires that every action in email digest is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | In Progress | Unresolved | Low | Notifications | hotfix, security | Rahul Verma | Priya Sharma | Sprint 43 | 1 | PROJ-1084 |  | 2026-08-02 17:46 | 2026-08-07 17:46 |  | 2026-08-25 | 2 | [2026-08-03 15:46] Sofia Rossi: Rollback performed; issue no longer occurring in prod. [2026-08-04 20:46] Lucas Martin: Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1087 | Bug | Login broken on Safari 17 | Login does not work on Safari 17 (macOS and iOS). Console shows 'TypeError: undefined is not an object'. Works fine on Chrome and Firefox. | Done | Fixed | Medium | Auth | customer-reported, security | Sofia Rossi | Omar Haddad | Sprint 43 | 13 | PROJ-1001 | 2026.08.2 | 2026-08-03 15:24 | 2026-08-11 21:24 | 2026-08-11 21:24 | 2026-08-23 | 5 | [2026-08-03 21:24] Kenji Tanaka: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-08-04 04:24] Omar Haddad: QA verified on staging, looks good. [2026-08-06 05:24] Chloe Nguyen: Root cause identified: cache key did not include tenant id. [2026-08-06 16:24] Sofia Rossi: Discussed in standup — we'll pick this up after the current hotfix. [2026-08-08 17:24] Sofia Rossi: Root cause: missing null check when the auth config is not loaded.
PROJ-1088 | Story | Support localisation for refund flow | Refund flow must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | Done | Fixed | Low | Payments |  | Lucas Martin | Chloe Nguyen | Sprint 43 | 2 |  | 2026.08.2 | 2026-09-09 10:18 | 2026-09-20 11:18 | 2026-09-20 11:18 | 2026-09-24 | 4 | [2026-09-10 09:18] Chloe Nguyen: Root cause: missing null check when the payments config is not loaded. [2026-09-11 07:18] Chloe Nguyen: Moved to backlog — lower priority than the Mobile work this sprint. [2026-09-11 09:18] Lucas Martin: Could not reproduce on latest build. Can the reporter confirm? [2026-09-12 16:18] Chloe Nguyen: Design mockups attached. Please review before we start.
PROJ-1089 | Story | Support localisation for SMS alerts | SMS alerts must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | To Do | Unresolved | Highest | Notifications | hotfix, ux | Chloe Nguyen | Aarav Mehta | Sprint 42 | 2 | PROJ-1029 |  | 2026-09-13 15:49 | 2026-09-23 18:49 |  | 2026-09-21 | 5 | [2026-09-15 15:49] Aarav Mehta: QA verified on staging, looks good. [2026-09-17 11:49] Daniel Ortiz: Code review done, left a few minor comments. LGTM otherwise. [2026-09-19 01:49] Aarav Mehta: Security team signed off on the approach. [2026-09-19 07:49] Aarav Mehta: Merged to main. Will be in release 2026.08.2. [2026-09-19 11:49] Chloe Nguyen: Performance test results: p95 down from 2.4s to 280ms.
PROJ-1090 | Bug | Crash when using CDN config with empty input | Submitting CDN config with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | Done | Fixed | Low | Infra | hotfix, performance, customer-reported | Kenji Tanaka | Chloe Nguyen | Sprint 45 | 8 |  | 2026.09.1 | 2026-08-18 12:33 | 2026-08-25 17:33 | 2026-08-25 17:33 | 2026-09-05 | 4 | [2026-08-19 00:33] Kenji Tanaka: Code review done, left a few minor comments. LGTM otherwise. [2026-08-20 16:33] Kenji Tanaka: Discussed in standup — we'll pick this up after the current hotfix. [2026-08-21 07:33] Daniel Ortiz: Product confirmed this is expected behaviour; closing as Won't Fix. [2026-08-22 22:33] Chloe Nguyen: Customer Wayne Enterprises is also asking about this; marking as high visibility.
PROJ-1091 | Story | Add audit logging to session timeout | Compliance requires that every action in session timeout is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | Blocked | Unresolved | High | Auth | tech-debt | Lucas Martin | Omar Haddad | Sprint 45 | 8 |  |  | 2026-08-31 11:14 | 2026-09-14 17:14 |  | 2026-09-26 | 3 | [2026-08-31 23:14] Omar Haddad: Security team signed off on the approach. [2026-09-01 07:14] Omar Haddad: I can reproduce this on staging. Attaching HAR file. [2026-09-02 15:14] Daniel Ortiz: Duplicate of PROJ-1062. Closing this one.
PROJ-1092 | Story | Support localisation for session timeout | Session timeout must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | In Review | Unresolved | Low | Auth |  | Rahul Verma | Chloe Nguyen | Sprint 43 | 5 | PROJ-1062 | 2026.09.1 | 2026-07-30 16:50 | 2026-08-12 22:50 |  | 2026-08-17 | 2 | [2026-08-02 04:50] Aarav Mehta: Is this blocking the release or can it slip to next sprint? [2026-08-04 05:50] Sofia Rossi: I can reproduce this on staging. Attaching HAR file.
PROJ-1093 | Bug | Crash when using iOS app launch with empty input | Submitting iOS app launch with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | In Progress | Unresolved | Low | Mobile | tech-debt, hotfix, performance | Emma Clarke | Rahul Verma | Sprint 45 | 3 |  |  | 2026-09-17 13:43 | 2026-09-24 16:43 |  | 2026-10-07 | 5 | [2026-09-18 13:43] Sofia Rossi: Root cause identified: cache key did not include tenant id. [2026-09-19 16:43] Rahul Verma: Could not reproduce on latest build. Can the reporter confirm? [2026-09-21 22:43] Rahul Verma: Added more logging, will check again after tomorrow's deploy. [2026-09-23 14:43] Daniel Ortiz: Looping in Rahul Verma since they own this area. [2026-09-24 23:43] Omar Haddad: Design mockups attached. Please review before we start.
PROJ-1094 | Bug | Unsubscribe link fails intermittently in production | Users report that unsubscribe link fails roughly 1 in 20 attempts. Error logs show a 500 from the Notifications service. Steps: 1) Log in 2) Trigger unsubscribe link 3) Observe error toast. Expected: operation succeeds. | In Progress | Unresolved | Medium | Notifications | customer-reported | Priya Sharma | Daniel Ortiz | Sprint 44 | 13 |  |  | 2026-08-05 15:22 | 2026-08-16 21:22 |  | 2026-08-24 | 1 | [2026-08-07 04:22] Priya Sharma: QA verified on staging, looks good.
PROJ-1095 | Bug | Crash when using password reset with empty input | Submitting password reset with an empty payload causes an unhandled exception and a blank screen. Need input validation and a friendly error message. | To Do | Unresolved | Highest | Auth | q4-goal, performance, security | Emma Clarke | Kenji Tanaka | Sprint 42 | 3 |  |  | 2026-09-04 13:56 | 2026-09-13 17:56 |  | 2026-10-03 | 4 | [2026-09-06 10:56] Sofia Rossi: Design mockups attached. Please review before we start. [2026-09-08 08:56] Kenji Tanaka: Code review done, left a few minor comments. LGTM otherwise. [2026-09-09 11:56] Sofia Rossi: Security team signed off on the approach. [2026-09-10 06:56] Kenji Tanaka: Customer Umbrella Ltd is also asking about this; marking as high visibility.
PROJ-1096 | Bug | Unsubscribe link fails intermittently in production | Users report that unsubscribe link fails roughly 1 in 20 attempts. Error logs show a 500 from the Notifications service. Steps: 1) Log in 2) Trigger unsubscribe link 3) Observe error toast. Expected: operation succeeds. | To Do | Unresolved | Highest | Notifications | hotfix, performance | Aarav Mehta | Lucas Martin |  | 5 | PROJ-1098 |  | 2026-09-08 09:54 | 2026-09-16 14:54 |  | 2026-10-04 | 5 | [2026-09-09 04:54] Aarav Mehta: Root cause identified: cache key did not include tenant id. [2026-09-10 04:54] Lucas Martin: Root cause identified: cache key did not include tenant id. [2026-09-12 01:54] Aarav Mehta: PR is up for review: https://git.example.com/notifications/pull/203 [2026-09-12 18:54] Aarav Mehta: Merged to main. Will be in release 2026.09.0. [2026-09-14 16:54] Lucas Martin: Root cause: missing null check when the notifications config is not loaded.
PROJ-1097 | Story | Add audit logging to dashboard widgets | Compliance requires that every action in dashboard widgets is written to the audit log with user id, timestamp, IP and before/after values. Retain for 7 years. | To Do | Unresolved | Low | Reporting | hotfix, tech-debt | Lucas Martin | Daniel Ortiz | Sprint 42 | 3 |  |  | 2026-07-23 15:31 | 2026-07-26 23:31 |  | 2026-08-16 | 5 | [2026-07-23 20:31] Lucas Martin: Root cause identified: cache key did not include tenant id. [2026-07-25 21:31] Daniel Ortiz: Could not reproduce on latest build. Can the reporter confirm? [2026-07-26 21:31] Emma Clarke: Security team signed off on the approach. [2026-07-28 07:31] Daniel Ortiz: Moved to backlog — lower priority than the API work this sprint. [2026-07-30 01:31] Lucas Martin: Could not reproduce on latest build. Can the reporter confirm?
PROJ-1098 | Story | Support localisation for offline mode | Offline mode must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | In Progress | Unresolved | Medium | Mobile |  | Lucas Martin | Kenji Tanaka | Sprint 43 | 2 |  |  | 2026-08-16 17:28 | 2026-08-23 19:28 |  | 2026-08-28 | 3 | [2026-08-18 18:28] Kenji Tanaka: Is this blocking the release or can it slip to next sprint? [2026-08-18 21:28] Lucas Martin: Root cause identified: cache key did not include tenant id. [2026-08-19 13:28] Aarav Mehta: Code review done, left a few minor comments. LGTM otherwise.
PROJ-1099 | Story | Support localisation for dark mode | Dark mode must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | Blocked | Unresolved | Medium | Mobile | ux, security | Chloe Nguyen | Daniel Ortiz | Sprint 45 | 8 | PROJ-1012 |  | 2026-07-23 16:40 | 2026-08-04 22:40 |  | 2026-08-15 | 4 | [2026-07-24 13:40] Chloe Nguyen: Root cause: missing null check when the mobile config is not loaded. [2026-07-25 09:40] Chloe Nguyen: Moved to backlog — lower priority than the Reporting work this sprint. [2026-07-27 01:40] Daniel Ortiz: Code review done, left a few minor comments. LGTM otherwise. [2026-07-29 00:40] Sofia Rossi: Performance test results: p95 down from 2.4s to 280ms.
PROJ-1100 | Story | Support localisation for scheduled reports | Scheduled reports must support English, Spanish, German and Japanese. Extract strings to the i18n bundle and handle right-to-left layout for future Arabic support. | Done | Fixed | Medium | Reporting | performance, ux, hotfix | Daniel Ortiz | Priya Sharma | Sprint 43 | 5 | PROJ-1003 | 2026.09.1 | 2026-07-18 13:07 | 2026-07-29 20:07 | 2026-07-29 20:07 | 2026-08-13 | 2 | [2026-07-18 18:07] Lucas Martin: This depends on PROJ-1092 being completed first. [2026-07-18 20:07] Daniel Ortiz: Code review done, left a few minor comments. LGTM otherwise.

## Comments
Issue Key | Comment # | Author | Created | Comment
PROJ-1001 | 1 | Chloe Nguyen | 2026-09-15 19:02 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1001 | 2 | Chloe Nguyen | 2026-09-16 10:02 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1001 | 3 | Sofia Rossi | 2026-09-18 10:02 | Design mockups attached. Please review before we start.
PROJ-1001 | 4 | Lucas Martin | 2026-09-18 16:02 | Looping in Sofia Rossi since they own this area.
PROJ-1001 | 5 | Daniel Ortiz | 2026-09-20 23:02 | Root cause: missing null check when the payments config is not loaded.
PROJ-1002 | 1 | Sofia Rossi | 2026-08-12 00:14 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1002 | 2 | Daniel Ortiz | 2026-08-13 13:14 | This depends on PROJ-1029 being completed first.
PROJ-1002 | 3 | Rahul Verma | 2026-08-14 22:14 | Is this blocking the release or can it slip to next sprint?
PROJ-1003 | 1 | Daniel Ortiz | 2026-08-14 20:18 | Customer Acme Corp is also asking about this; marking as high visibility.
PROJ-1003 | 2 | Chloe Nguyen | 2026-08-16 23:18 | Rollback performed; issue no longer occurring in prod.
PROJ-1003 | 3 | Lucas Martin | 2026-08-17 04:18 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1004 | 1 | Rahul Verma | 2026-08-28 08:28 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1004 | 2 | Emma Clarke | 2026-08-29 18:28 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1005 | 1 | Aarav Mehta | 2026-07-09 08:46 | Is this blocking the release or can it slip to next sprint?
PROJ-1005 | 2 | Priya Sharma | 2026-07-10 12:46 | Moved to backlog — lower priority than the Search work this sprint.
PROJ-1005 | 3 | Aarav Mehta | 2026-07-11 06:46 | Design mockups attached. Please review before we start.
PROJ-1005 | 4 | Lucas Martin | 2026-07-11 11:46 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1006 | 1 | Sofia Rossi | 2026-09-12 06:37 | PR is up for review: https://git.example.com/auth/pull/371
PROJ-1006 | 2 | Sofia Rossi | 2026-09-12 08:37 | Design mockups attached. Please review before we start.
PROJ-1006 | 3 | Sofia Rossi | 2026-09-14 18:37 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1007 | 1 | Rahul Verma | 2026-08-13 16:43 | I can reproduce this on staging. Attaching HAR file.
PROJ-1007 | 2 | Kenji Tanaka | 2026-08-13 18:43 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1007 | 3 | Sofia Rossi | 2026-08-14 23:43 | Added more logging, will check again after tomorrow's deploy.
PROJ-1008 | 1 | Daniel Ortiz | 2026-07-05 13:47 | Looping in Lucas Martin since they own this area.
PROJ-1009 | 1 | Chloe Nguyen | 2026-09-08 19:01 | Duplicate of PROJ-1006. Closing this one.
PROJ-1009 | 2 | Priya Sharma | 2026-09-10 06:01 | This depends on PROJ-1085 being completed first.
PROJ-1009 | 3 | Kenji Tanaka | 2026-09-12 17:01 | QA verified on staging, looks good.
PROJ-1010 | 1 | Kenji Tanaka | 2026-08-23 00:53 | Design mockups attached. Please review before we start.
PROJ-1010 | 2 | Omar Haddad | 2026-08-24 10:53 | Security team signed off on the approach.
PROJ-1010 | 3 | Omar Haddad | 2026-08-24 14:53 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1011 | 1 | Rahul Verma | 2026-07-31 00:51 | Duplicate of PROJ-1021. Closing this one.
PROJ-1011 | 2 | Priya Sharma | 2026-07-31 18:51 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1011 | 3 | Daniel Ortiz | 2026-08-01 13:51 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1011 | 4 | Rahul Verma | 2026-08-02 04:51 | Is this blocking the release or can it slip to next sprint?
PROJ-1011 | 5 | Rahul Verma | 2026-08-03 06:51 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1012 | 1 | Daniel Ortiz | 2026-08-29 16:39 | Merged to main. Will be in release 2026.09.1.
PROJ-1012 | 2 | Priya Sharma | 2026-08-31 18:39 | Estimating at 2 story points after refinement.
PROJ-1013 | 1 | Kenji Tanaka | 2026-08-04 11:10 | Root cause identified: cache key did not include tenant id.
PROJ-1013 | 2 | Chloe Nguyen | 2026-08-06 03:10 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1013 | 3 | Sofia Rossi | 2026-08-07 02:10 | I can reproduce this on staging. Attaching HAR file.
PROJ-1013 | 4 | Sofia Rossi | 2026-08-07 15:10 | Rollback performed; issue no longer occurring in prod.
PROJ-1013 | 5 | Sofia Rossi | 2026-08-08 13:10 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1014 | 1 | Chloe Nguyen | 2026-07-04 21:12 | I can reproduce this on staging. Attaching HAR file.
PROJ-1014 | 2 | Chloe Nguyen | 2026-07-06 05:12 | This depends on PROJ-1090 being completed first.
PROJ-1014 | 3 | Chloe Nguyen | 2026-07-07 02:12 | Merged to main. Will be in release 2026.08.2.
PROJ-1014 | 4 | Kenji Tanaka | 2026-07-07 15:12 | PR is up for review: https://git.example.com/search/pull/595
PROJ-1015 | 1 | Daniel Ortiz | 2026-07-20 01:06 | Moved to backlog — lower priority than the Auth work this sprint.
PROJ-1015 | 2 | Aarav Mehta | 2026-07-20 22:06 | Is this blocking the release or can it slip to next sprint?
PROJ-1015 | 3 | Sofia Rossi | 2026-07-23 07:06 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1016 | 1 | Aarav Mehta | 2026-09-17 12:18 | PR is up for review: https://git.example.com/reporting/pull/657
PROJ-1016 | 2 | Lucas Martin | 2026-09-18 00:18 | QA verified on staging, looks good.
PROJ-1016 | 3 | Rahul Verma | 2026-09-18 21:18 | Root cause identified: cache key did not include tenant id.
PROJ-1016 | 4 | Kenji Tanaka | 2026-09-20 22:18 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1016 | 5 | Rahul Verma | 2026-09-21 02:18 | Customer Stark Industries is also asking about this; marking as high visibility.
PROJ-1017 | 1 | Sofia Rossi | 2026-08-25 01:18 | Rollback performed; issue no longer occurring in prod.
PROJ-1017 | 2 | Emma Clarke | 2026-08-26 02:18 | Duplicate of PROJ-1071. Closing this one.
PROJ-1017 | 3 | Daniel Ortiz | 2026-08-27 08:18 | Moved to backlog — lower priority than the Search work this sprint.
PROJ-1017 | 4 | Emma Clarke | 2026-08-28 21:18 | Estimating at 8 story points after refinement.
PROJ-1018 | 1 | Lucas Martin | 2026-09-10 10:24 | Rollback performed; issue no longer occurring in prod.
PROJ-1018 | 2 | Sofia Rossi | 2026-09-11 10:24 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1018 | 3 | Lucas Martin | 2026-09-12 12:24 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1018 | 4 | Sofia Rossi | 2026-09-12 16:24 | Added more logging, will check again after tomorrow's deploy.
PROJ-1019 | 1 | Priya Sharma | 2026-07-11 18:54 | Duplicate of PROJ-1056. Closing this one.
PROJ-1019 | 2 | Rahul Verma | 2026-07-13 17:54 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1019 | 3 | Emma Clarke | 2026-07-14 17:54 | Root cause: missing null check when the infra config is not loaded.
PROJ-1019 | 4 | Rahul Verma | 2026-07-16 10:54 | Root cause identified: cache key did not include tenant id.
PROJ-1019 | 5 | Emma Clarke | 2026-07-17 04:54 | Security team signed off on the approach.
PROJ-1020 | 1 | Sofia Rossi | 2026-09-15 02:36 | Duplicate of PROJ-1082. Closing this one.
PROJ-1021 | 1 | Omar Haddad | 2026-07-19 17:58 | Customer Umbrella Ltd is also asking about this; marking as high visibility.
PROJ-1021 | 2 | Omar Haddad | 2026-07-21 19:58 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1021 | 3 | Aarav Mehta | 2026-07-23 02:58 | Root cause: missing null check when the search config is not loaded.
PROJ-1022 | 1 | Rahul Verma | 2026-07-17 07:02 | This depends on PROJ-1063 being completed first.
PROJ-1022 | 2 | Emma Clarke | 2026-07-18 02:02 | Looping in Emma Clarke since they own this area.
PROJ-1022 | 3 | Priya Sharma | 2026-07-20 13:02 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1023 | 1 | Sofia Rossi | 2026-09-09 22:37 | This depends on PROJ-1046 being completed first.
PROJ-1023 | 2 | Priya Sharma | 2026-09-10 20:37 | I can reproduce this on staging. Attaching HAR file.
PROJ-1024 | 1 | Omar Haddad | 2026-08-08 22:41 | Is this blocking the release or can it slip to next sprint?
PROJ-1024 | 2 | Priya Sharma | 2026-08-10 21:41 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1024 | 3 | Chloe Nguyen | 2026-08-12 16:41 | This depends on PROJ-1059 being completed first.
PROJ-1024 | 4 | Aarav Mehta | 2026-08-14 16:41 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1025 | 1 | Kenji Tanaka | 2026-09-11 05:42 | Added more logging, will check again after tomorrow's deploy.
PROJ-1025 | 2 | Chloe Nguyen | 2026-09-11 21:42 | Estimating at 2 story points after refinement.
PROJ-1025 | 3 | Daniel Ortiz | 2026-09-13 19:42 | QA verified on staging, looks good.
PROJ-1025 | 4 | Omar Haddad | 2026-09-15 13:42 | I can reproduce this on staging. Attaching HAR file.
PROJ-1025 | 5 | Omar Haddad | 2026-09-16 14:42 | QA verified on staging, looks good.
PROJ-1026 | 1 | Sofia Rossi | 2026-07-15 16:27 | PR is up for review: https://git.example.com/reporting/pull/885
PROJ-1027 | 1 | Priya Sharma | 2026-08-20 12:27 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1027 | 2 | Emma Clarke | 2026-08-22 03:27 | Root cause identified: cache key did not include tenant id.
PROJ-1027 | 3 | Emma Clarke | 2026-08-23 13:27 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1027 | 4 | Priya Sharma | 2026-08-23 21:27 | Added more logging, will check again after tomorrow's deploy.
PROJ-1028 | 1 | Omar Haddad | 2026-07-21 23:04 | Design mockups attached. Please review before we start.
PROJ-1028 | 2 | Omar Haddad | 2026-07-23 01:04 | Design mockups attached. Please review before we start.
PROJ-1028 | 3 | Sofia Rossi | 2026-07-24 11:04 | Added more logging, will check again after tomorrow's deploy.
PROJ-1029 | 1 | Aarav Mehta | 2026-09-19 21:04 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1029 | 2 | Omar Haddad | 2026-09-21 16:04 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1029 | 3 | Omar Haddad | 2026-09-22 17:04 | QA verified on staging, looks good.
PROJ-1030 | 1 | Emma Clarke | 2026-09-16 21:09 | Duplicate of PROJ-1040. Closing this one.
PROJ-1030 | 2 | Sofia Rossi | 2026-09-17 22:09 | Security team signed off on the approach.
PROJ-1031 | 1 | Chloe Nguyen | 2026-08-08 16:48 | Design mockups attached. Please review before we start.
PROJ-1031 | 2 | Priya Sharma | 2026-08-09 17:48 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1032 | 1 | Daniel Ortiz | 2026-09-16 23:27 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1032 | 2 | Chloe Nguyen | 2026-09-18 16:27 | Root cause: missing null check when the api config is not loaded.
PROJ-1032 | 3 | Kenji Tanaka | 2026-09-20 02:27 | Rollback performed; issue no longer occurring in prod.
PROJ-1032 | 4 | Emma Clarke | 2026-09-20 05:27 | Root cause: missing null check when the api config is not loaded.
PROJ-1033 | 1 | Aarav Mehta | 2026-08-29 12:18 | This depends on PROJ-1100 being completed first.
PROJ-1033 | 2 | Priya Sharma | 2026-08-30 11:18 | Merged to main. Will be in release 2026.09.1.
PROJ-1033 | 3 | Daniel Ortiz | 2026-09-01 09:18 | Moved to backlog — lower priority than the Payments work this sprint.
PROJ-1033 | 4 | Omar Haddad | 2026-09-02 21:18 | QA verified on staging, looks good.
PROJ-1033 | 5 | Daniel Ortiz | 2026-09-04 02:18 | Customer Initech is also asking about this; marking as high visibility.
PROJ-1034 | 1 | Daniel Ortiz | 2026-07-06 17:04 | Is this blocking the release or can it slip to next sprint?
PROJ-1034 | 2 | Kenji Tanaka | 2026-07-07 02:04 | I can reproduce this on staging. Attaching HAR file.
PROJ-1034 | 3 | Lucas Martin | 2026-07-08 08:04 | PR is up for review: https://git.example.com/infra/pull/810
PROJ-1035 | 1 | Daniel Ortiz | 2026-08-09 17:54 | Moved to backlog — lower priority than the API work this sprint.
PROJ-1035 | 2 | Chloe Nguyen | 2026-08-12 03:54 | Is this blocking the release or can it slip to next sprint?
PROJ-1036 | 1 | Kenji Tanaka | 2026-07-18 15:32 | Rollback performed; issue no longer occurring in prod.
PROJ-1036 | 2 | Omar Haddad | 2026-07-20 03:32 | Is this blocking the release or can it slip to next sprint?
PROJ-1037 | 1 | Omar Haddad | 2026-09-14 13:39 | Looping in Daniel Ortiz since they own this area.
PROJ-1038 | 1 | Emma Clarke | 2026-09-10 18:20 | Looping in Kenji Tanaka since they own this area.
PROJ-1038 | 2 | Emma Clarke | 2026-09-12 18:20 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1039 | 1 | Rahul Verma | 2026-09-02 20:18 | Root cause identified: cache key did not include tenant id.
PROJ-1039 | 2 | Kenji Tanaka | 2026-09-04 02:18 | This depends on PROJ-1013 being completed first.
PROJ-1039 | 3 | Aarav Mehta | 2026-09-06 06:18 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1040 | 1 | Omar Haddad | 2026-08-12 13:10 | Security team signed off on the approach.
PROJ-1040 | 2 | Chloe Nguyen | 2026-08-13 05:10 | Looping in Omar Haddad since they own this area.
PROJ-1040 | 3 | Daniel Ortiz | 2026-08-14 19:10 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1041 | 1 | Lucas Martin | 2026-08-12 00:29 | QA verified on staging, looks good.
PROJ-1041 | 2 | Lucas Martin | 2026-08-13 13:29 | Merged to main. Will be in release 2026.10.0.
PROJ-1041 | 3 | Lucas Martin | 2026-08-13 17:29 | QA verified on staging, looks good.
PROJ-1042 | 1 | Chloe Nguyen | 2026-07-31 13:06 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1042 | 2 | Sofia Rossi | 2026-08-02 08:06 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1043 | 1 | Priya Sharma | 2026-08-13 08:29 | PR is up for review: https://git.example.com/search/pull/266
PROJ-1043 | 2 | Rahul Verma | 2026-08-14 22:29 | Security team signed off on the approach.
PROJ-1043 | 3 | Priya Sharma | 2026-08-15 06:29 | Customer Umbrella Ltd is also asking about this; marking as high visibility.
PROJ-1043 | 4 | Emma Clarke | 2026-08-17 08:29 | Merged to main. Will be in release 2026.10.0.
PROJ-1044 | 1 | Kenji Tanaka | 2026-08-09 16:39 | This depends on PROJ-1068 being completed first.
PROJ-1044 | 2 | Emma Clarke | 2026-08-12 04:39 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1044 | 3 | Kenji Tanaka | 2026-08-13 10:39 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1044 | 4 | Priya Sharma | 2026-08-14 20:39 | Estimating at 8 story points after refinement.
PROJ-1045 | 1 | Aarav Mehta | 2026-08-30 19:18 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1045 | 2 | Priya Sharma | 2026-09-01 21:18 | I can reproduce this on staging. Attaching HAR file.
PROJ-1045 | 3 | Aarav Mehta | 2026-09-02 21:18 | Added more logging, will check again after tomorrow's deploy.
PROJ-1045 | 4 | Priya Sharma | 2026-09-03 12:18 | Is this blocking the release or can it slip to next sprint?
PROJ-1045 | 5 | Priya Sharma | 2026-09-04 18:18 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1046 | 1 | Kenji Tanaka | 2026-08-06 07:35 | Estimating at 3 story points after refinement.
PROJ-1046 | 2 | Kenji Tanaka | 2026-08-08 15:35 | Added more logging, will check again after tomorrow's deploy.
PROJ-1046 | 3 | Kenji Tanaka | 2026-08-09 06:35 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1046 | 4 | Kenji Tanaka | 2026-08-11 03:35 | Duplicate of PROJ-1062. Closing this one.
PROJ-1046 | 5 | Omar Haddad | 2026-08-12 00:35 | I can reproduce this on staging. Attaching HAR file.
PROJ-1047 | 1 | Chloe Nguyen | 2026-08-04 15:32 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1047 | 2 | Kenji Tanaka | 2026-08-06 06:32 | Estimating at 3 story points after refinement.
PROJ-1048 | 1 | Sofia Rossi | 2026-07-24 16:10 | I can reproduce this on staging. Attaching HAR file.
PROJ-1049 | 1 | Aarav Mehta | 2026-07-03 22:35 | Customer Acme Corp is also asking about this; marking as high visibility.
PROJ-1049 | 2 | Sofia Rossi | 2026-07-06 04:35 | Root cause: missing null check when the mobile config is not loaded.
PROJ-1049 | 3 | Rahul Verma | 2026-07-06 20:35 | QA verified on staging, looks good.
PROJ-1049 | 4 | Emma Clarke | 2026-07-08 04:35 | Looping in Aarav Mehta since they own this area.
PROJ-1050 | 1 | Daniel Ortiz | 2026-09-09 06:11 | Customer Globex is also asking about this; marking as high visibility.
PROJ-1051 | 1 | Rahul Verma | 2026-08-13 05:40 | Root cause identified: cache key did not include tenant id.
PROJ-1051 | 2 | Rahul Verma | 2026-08-15 04:40 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1051 | 3 | Chloe Nguyen | 2026-08-16 10:40 | Root cause: missing null check when the mobile config is not loaded.
PROJ-1051 | 4 | Rahul Verma | 2026-08-17 20:40 | Estimating at 2 story points after refinement.
PROJ-1051 | 5 | Rahul Verma | 2026-08-19 00:40 | Root cause identified: cache key did not include tenant id.
PROJ-1052 | 1 | Emma Clarke | 2026-08-04 19:46 | Duplicate of PROJ-1039. Closing this one.
PROJ-1052 | 2 | Lucas Martin | 2026-08-06 17:46 | PR is up for review: https://git.example.com/api/pull/281
PROJ-1052 | 3 | Sofia Rossi | 2026-08-08 21:46 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1053 | 1 | Lucas Martin | 2026-08-09 14:52 | Root cause identified: cache key did not include tenant id.
PROJ-1053 | 2 | Sofia Rossi | 2026-08-11 12:52 | This depends on PROJ-1022 being completed first.
PROJ-1053 | 3 | Sofia Rossi | 2026-08-13 02:52 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1053 | 4 | Lucas Martin | 2026-08-14 12:52 | Rollback performed; issue no longer occurring in prod.
PROJ-1054 | 1 | Priya Sharma | 2026-07-21 14:19 | Design mockups attached. Please review before we start.
PROJ-1054 | 2 | Omar Haddad | 2026-07-23 19:19 | Customer Stark Industries is also asking about this; marking as high visibility.
PROJ-1054 | 3 | Priya Sharma | 2026-07-24 11:19 | Root cause identified: cache key did not include tenant id.
PROJ-1054 | 4 | Priya Sharma | 2026-07-25 17:19 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1055 | 1 | Lucas Martin | 2026-08-13 03:39 | Duplicate of PROJ-1031. Closing this one.
PROJ-1055 | 2 | Chloe Nguyen | 2026-08-13 16:39 | Root cause: missing null check when the search config is not loaded.
PROJ-1055 | 3 | Chloe Nguyen | 2026-08-15 10:39 | This depends on PROJ-1024 being completed first.
PROJ-1056 | 1 | Lucas Martin | 2026-08-22 19:26 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1056 | 2 | Omar Haddad | 2026-08-24 20:26 | Moved to backlog — lower priority than the Reporting work this sprint.
PROJ-1056 | 3 | Omar Haddad | 2026-08-26 08:26 | Looping in Lucas Martin since they own this area.
PROJ-1056 | 4 | Omar Haddad | 2026-08-27 02:26 | Root cause: missing null check when the auth config is not loaded.
PROJ-1056 | 5 | Omar Haddad | 2026-08-28 02:26 | Duplicate of PROJ-1008. Closing this one.
PROJ-1057 | 1 | Omar Haddad | 2026-09-06 17:08 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1057 | 2 | Emma Clarke | 2026-09-08 11:08 | Is this blocking the release or can it slip to next sprint?
PROJ-1057 | 3 | Omar Haddad | 2026-09-08 13:08 | Is this blocking the release or can it slip to next sprint?
PROJ-1058 | 1 | Emma Clarke | 2026-07-07 23:06 | Added more logging, will check again after tomorrow's deploy.
PROJ-1058 | 2 | Priya Sharma | 2026-07-09 19:06 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1058 | 3 | Aarav Mehta | 2026-07-10 03:06 | I can reproduce this on staging. Attaching HAR file.
PROJ-1058 | 4 | Priya Sharma | 2026-07-11 02:06 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1059 | 1 | Omar Haddad | 2026-07-11 14:36 | Design mockups attached. Please review before we start.
PROJ-1059 | 2 | Aarav Mehta | 2026-07-13 18:36 | Added more logging, will check again after tomorrow's deploy.
PROJ-1059 | 3 | Daniel Ortiz | 2026-07-16 04:36 | QA verified on staging, looks good.
PROJ-1059 | 4 | Daniel Ortiz | 2026-07-17 13:36 | Root cause identified: cache key did not include tenant id.
PROJ-1059 | 5 | Daniel Ortiz | 2026-07-18 15:36 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1060 | 1 | Rahul Verma | 2026-08-25 20:44 | Added more logging, will check again after tomorrow's deploy.
PROJ-1060 | 2 | Kenji Tanaka | 2026-08-28 04:44 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1061 | 1 | Emma Clarke | 2026-09-07 00:10 | Is this blocking the release or can it slip to next sprint?
PROJ-1061 | 2 | Emma Clarke | 2026-09-08 09:10 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1061 | 3 | Aarav Mehta | 2026-09-08 13:10 | I can reproduce this on staging. Attaching HAR file.
PROJ-1062 | 1 | Kenji Tanaka | 2026-07-18 20:43 | QA verified on staging, looks good.
PROJ-1062 | 2 | Priya Sharma | 2026-07-21 00:43 | QA verified on staging, looks good.
PROJ-1062 | 3 | Aarav Mehta | 2026-07-21 11:43 | I can reproduce this on staging. Attaching HAR file.
PROJ-1063 | 1 | Kenji Tanaka | 2026-07-12 15:58 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1063 | 2 | Daniel Ortiz | 2026-07-14 13:58 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1063 | 3 | Daniel Ortiz | 2026-07-15 00:58 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1063 | 4 | Kenji Tanaka | 2026-07-16 06:58 | QA verified on staging, looks good.
PROJ-1064 | 1 | Priya Sharma | 2026-08-08 22:52 | I can reproduce this on staging. Attaching HAR file.
PROJ-1064 | 2 | Emma Clarke | 2026-08-10 13:52 | Merged to main. Will be in release 2026.08.2.
PROJ-1065 | 1 | Aarav Mehta | 2026-08-19 08:11 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1065 | 2 | Aarav Mehta | 2026-08-19 18:11 | Estimating at 3 story points after refinement.
PROJ-1065 | 3 | Aarav Mehta | 2026-08-21 06:11 | Moved to backlog — lower priority than the Reporting work this sprint.
PROJ-1065 | 4 | Lucas Martin | 2026-08-22 22:11 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1065 | 5 | Lucas Martin | 2026-08-24 18:11 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1066 | 1 | Daniel Ortiz | 2026-07-25 19:34 | Rollback performed; issue no longer occurring in prod.
PROJ-1066 | 2 | Emma Clarke | 2026-07-26 00:34 | I can reproduce this on staging. Attaching HAR file.
PROJ-1067 | 1 | Rahul Verma | 2026-08-12 09:45 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1068 | 1 | Emma Clarke | 2026-08-27 14:16 | Root cause identified: cache key did not include tenant id.
PROJ-1069 | 1 | Daniel Ortiz | 2026-07-12 09:18 | Is this blocking the release or can it slip to next sprint?
PROJ-1069 | 2 | Chloe Nguyen | 2026-07-14 19:18 | Estimating at 3 story points after refinement.
PROJ-1070 | 1 | Chloe Nguyen | 2026-08-17 17:27 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1071 | 1 | Aarav Mehta | 2026-09-12 13:09 | This depends on PROJ-1051 being completed first.
PROJ-1071 | 2 | Kenji Tanaka | 2026-09-14 03:09 | Rollback performed; issue no longer occurring in prod.
PROJ-1071 | 3 | Daniel Ortiz | 2026-09-16 08:09 | PR is up for review: https://git.example.com/mobile/pull/533
PROJ-1071 | 4 | Sofia Rossi | 2026-09-17 02:09 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1071 | 5 | Daniel Ortiz | 2026-09-19 14:09 | I can reproduce this on staging. Attaching HAR file.
PROJ-1072 | 1 | Rahul Verma | 2026-08-03 19:41 | Root cause identified: cache key did not include tenant id.
PROJ-1072 | 2 | Kenji Tanaka | 2026-08-06 01:41 | QA verified on staging, looks good.
PROJ-1072 | 3 | Rahul Verma | 2026-08-07 07:41 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1072 | 4 | Rahul Verma | 2026-08-09 08:41 | Moved to backlog — lower priority than the Payments work this sprint.
PROJ-1073 | 1 | Aarav Mehta | 2026-08-17 01:17 | Moved to backlog — lower priority than the Reporting work this sprint.
PROJ-1073 | 2 | Sofia Rossi | 2026-08-17 04:17 | Root cause identified: cache key did not include tenant id.
PROJ-1073 | 3 | Daniel Ortiz | 2026-08-17 19:17 | Merged to main. Will be in release 2026.08.1.
PROJ-1073 | 4 | Aarav Mehta | 2026-08-20 00:17 | I can reproduce this on staging. Attaching HAR file.
PROJ-1074 | 1 | Chloe Nguyen | 2026-09-12 22:19 | Merged to main. Will be in release 2026.09.0.
PROJ-1074 | 2 | Emma Clarke | 2026-09-15 03:19 | Duplicate of PROJ-1038. Closing this one.
PROJ-1074 | 3 | Sofia Rossi | 2026-09-16 06:19 | Root cause identified: cache key did not include tenant id.
PROJ-1075 | 1 | Aarav Mehta | 2026-08-08 14:30 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1075 | 2 | Daniel Ortiz | 2026-08-10 05:30 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1075 | 3 | Chloe Nguyen | 2026-08-10 10:30 | Added more logging, will check again after tomorrow's deploy.
PROJ-1076 | 1 | Aarav Mehta | 2026-09-03 10:08 | Root cause: missing null check when the search config is not loaded.
PROJ-1076 | 2 | Rahul Verma | 2026-09-05 10:08 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1077 | 1 | Emma Clarke | 2026-08-13 18:56 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1077 | 2 | Priya Sharma | 2026-08-15 13:56 | Looping in Rahul Verma since they own this area.
PROJ-1077 | 3 | Omar Haddad | 2026-08-17 20:56 | I can reproduce this on staging. Attaching HAR file.
PROJ-1077 | 4 | Priya Sharma | 2026-08-19 04:56 | Added more logging, will check again after tomorrow's deploy.
PROJ-1078 | 1 | Priya Sharma | 2026-08-08 09:50 | Estimating at 8 story points after refinement.
PROJ-1078 | 2 | Chloe Nguyen | 2026-08-09 02:50 | I can reproduce this on staging. Attaching HAR file.
PROJ-1078 | 3 | Chloe Nguyen | 2026-08-11 02:50 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1079 | 1 | Daniel Ortiz | 2026-07-19 18:21 | Merged to main. Will be in release 2026.09.1.
PROJ-1079 | 2 | Omar Haddad | 2026-07-21 18:21 | Looping in Daniel Ortiz since they own this area.
PROJ-1079 | 3 | Omar Haddad | 2026-07-23 21:21 | Root cause: missing null check when the reporting config is not loaded.
PROJ-1079 | 4 | Chloe Nguyen | 2026-07-24 01:21 | Is this blocking the release or can it slip to next sprint?
PROJ-1080 | 1 | Daniel Ortiz | 2026-09-11 02:00 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1080 | 2 | Lucas Martin | 2026-09-12 08:00 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1080 | 3 | Omar Haddad | 2026-09-14 03:00 | I can reproduce this on staging. Attaching HAR file.
PROJ-1081 | 1 | Lucas Martin | 2026-08-12 19:49 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1081 | 2 | Lucas Martin | 2026-08-13 05:49 | Estimating at 3 story points after refinement.
PROJ-1082 | 1 | Rahul Verma | 2026-08-29 23:42 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1082 | 2 | Priya Sharma | 2026-08-31 15:42 | Duplicate of PROJ-1051. Closing this one.
PROJ-1082 | 3 | Chloe Nguyen | 2026-09-01 21:42 | Added more logging, will check again after tomorrow's deploy.
PROJ-1082 | 4 | Daniel Ortiz | 2026-09-02 12:42 | PR is up for review: https://git.example.com/mobile/pull/831
PROJ-1083 | 1 | Rahul Verma | 2026-08-07 10:51 | Customer Wayne Enterprises is also asking about this; marking as high visibility.
PROJ-1083 | 2 | Chloe Nguyen | 2026-08-08 10:51 | Design mockups attached. Please review before we start.
PROJ-1084 | 1 | Kenji Tanaka | 2026-09-19 05:53 | Customer Acme Corp is also asking about this; marking as high visibility.
PROJ-1085 | 1 | Omar Haddad | 2026-09-21 00:31 | Is this blocking the release or can it slip to next sprint?
PROJ-1085 | 2 | Aarav Mehta | 2026-09-22 20:31 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1086 | 1 | Sofia Rossi | 2026-08-03 15:46 | Rollback performed; issue no longer occurring in prod.
PROJ-1086 | 2 | Lucas Martin | 2026-08-04 20:46 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1087 | 1 | Kenji Tanaka | 2026-08-03 21:24 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1087 | 2 | Omar Haddad | 2026-08-04 04:24 | QA verified on staging, looks good.
PROJ-1087 | 3 | Chloe Nguyen | 2026-08-06 05:24 | Root cause identified: cache key did not include tenant id.
PROJ-1087 | 4 | Sofia Rossi | 2026-08-06 16:24 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1087 | 5 | Sofia Rossi | 2026-08-08 17:24 | Root cause: missing null check when the auth config is not loaded.
PROJ-1088 | 1 | Chloe Nguyen | 2026-09-10 09:18 | Root cause: missing null check when the payments config is not loaded.
PROJ-1088 | 2 | Chloe Nguyen | 2026-09-11 07:18 | Moved to backlog — lower priority than the Mobile work this sprint.
PROJ-1088 | 3 | Lucas Martin | 2026-09-11 09:18 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1088 | 4 | Chloe Nguyen | 2026-09-12 16:18 | Design mockups attached. Please review before we start.
PROJ-1089 | 1 | Aarav Mehta | 2026-09-15 15:49 | QA verified on staging, looks good.
PROJ-1089 | 2 | Daniel Ortiz | 2026-09-17 11:49 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1089 | 3 | Aarav Mehta | 2026-09-19 01:49 | Security team signed off on the approach.
PROJ-1089 | 4 | Aarav Mehta | 2026-09-19 07:49 | Merged to main. Will be in release 2026.08.2.
PROJ-1089 | 5 | Chloe Nguyen | 2026-09-19 11:49 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1090 | 1 | Kenji Tanaka | 2026-08-19 00:33 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1090 | 2 | Kenji Tanaka | 2026-08-20 16:33 | Discussed in standup — we'll pick this up after the current hotfix.
PROJ-1090 | 3 | Daniel Ortiz | 2026-08-21 07:33 | Product confirmed this is expected behaviour; closing as Won't Fix.
PROJ-1090 | 4 | Chloe Nguyen | 2026-08-22 22:33 | Customer Wayne Enterprises is also asking about this; marking as high visibility.
PROJ-1091 | 1 | Omar Haddad | 2026-08-31 23:14 | Security team signed off on the approach.
PROJ-1091 | 2 | Omar Haddad | 2026-09-01 07:14 | I can reproduce this on staging. Attaching HAR file.
PROJ-1091 | 3 | Daniel Ortiz | 2026-09-02 15:14 | Duplicate of PROJ-1062. Closing this one.
PROJ-1092 | 1 | Aarav Mehta | 2026-08-02 04:50 | Is this blocking the release or can it slip to next sprint?
PROJ-1092 | 2 | Sofia Rossi | 2026-08-04 05:50 | I can reproduce this on staging. Attaching HAR file.
PROJ-1093 | 1 | Sofia Rossi | 2026-09-18 13:43 | Root cause identified: cache key did not include tenant id.
PROJ-1093 | 2 | Rahul Verma | 2026-09-19 16:43 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1093 | 3 | Rahul Verma | 2026-09-21 22:43 | Added more logging, will check again after tomorrow's deploy.
PROJ-1093 | 4 | Daniel Ortiz | 2026-09-23 14:43 | Looping in Rahul Verma since they own this area.
PROJ-1093 | 5 | Omar Haddad | 2026-09-24 23:43 | Design mockups attached. Please review before we start.
PROJ-1094 | 1 | Priya Sharma | 2026-08-07 04:22 | QA verified on staging, looks good.
PROJ-1095 | 1 | Sofia Rossi | 2026-09-06 10:56 | Design mockups attached. Please review before we start.
PROJ-1095 | 2 | Kenji Tanaka | 2026-09-08 08:56 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1095 | 3 | Sofia Rossi | 2026-09-09 11:56 | Security team signed off on the approach.
PROJ-1095 | 4 | Kenji Tanaka | 2026-09-10 06:56 | Customer Umbrella Ltd is also asking about this; marking as high visibility.
PROJ-1096 | 1 | Aarav Mehta | 2026-09-09 04:54 | Root cause identified: cache key did not include tenant id.
PROJ-1096 | 2 | Lucas Martin | 2026-09-10 04:54 | Root cause identified: cache key did not include tenant id.
PROJ-1096 | 3 | Aarav Mehta | 2026-09-12 01:54 | PR is up for review: https://git.example.com/notifications/pull/203
PROJ-1096 | 4 | Aarav Mehta | 2026-09-12 18:54 | Merged to main. Will be in release 2026.09.0.
PROJ-1096 | 5 | Lucas Martin | 2026-09-14 16:54 | Root cause: missing null check when the notifications config is not loaded.
PROJ-1097 | 1 | Lucas Martin | 2026-07-23 20:31 | Root cause identified: cache key did not include tenant id.
PROJ-1097 | 2 | Daniel Ortiz | 2026-07-25 21:31 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1097 | 3 | Emma Clarke | 2026-07-26 21:31 | Security team signed off on the approach.
PROJ-1097 | 4 | Daniel Ortiz | 2026-07-28 07:31 | Moved to backlog — lower priority than the API work this sprint.
PROJ-1097 | 5 | Lucas Martin | 2026-07-30 01:31 | Could not reproduce on latest build. Can the reporter confirm?
PROJ-1098 | 1 | Kenji Tanaka | 2026-08-18 18:28 | Is this blocking the release or can it slip to next sprint?
PROJ-1098 | 2 | Lucas Martin | 2026-08-18 21:28 | Root cause identified: cache key did not include tenant id.
PROJ-1098 | 3 | Aarav Mehta | 2026-08-19 13:28 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1099 | 1 | Chloe Nguyen | 2026-07-24 13:40 | Root cause: missing null check when the mobile config is not loaded.
PROJ-1099 | 2 | Chloe Nguyen | 2026-07-25 09:40 | Moved to backlog — lower priority than the Reporting work this sprint.
PROJ-1099 | 3 | Daniel Ortiz | 2026-07-27 01:40 | Code review done, left a few minor comments. LGTM otherwise.
PROJ-1099 | 4 | Sofia Rossi | 2026-07-29 00:40 | Performance test results: p95 down from 2.4s to 280ms.
PROJ-1100 | 1 | Lucas Martin | 2026-07-18 18:07 | This depends on PROJ-1092 being completed first.
PROJ-1100 | 2 | Daniel Ortiz | 2026-07-18 20:07 | Code review done, left a few minor comments. LGTM otherwise.